BFUG (BE/AL) 21_9.6b

Issue date: 30/06/2010

BFUG Working Group

“International Openness -  The European Higher Education Area in a Global Context”

Work Plan for the period June 2010 - June 2012

agreed at the WG meeting on 27 May 2010

| General tasks | Who? | How? | When? |
| --- | --- | --- | --- |
| - To take forward the recommendations of “The European Higher Education Area (EHEA) in a global context: Report on overall developments at the European, national and institutional levels”. | See below |  |  |
| - To support the follow-up to the 2010 Bologna Policy Forum and the preparations of the 2012 Third Bologna Policy Forum. | See below |  |  |
| - To monitor the development of the EHEA Information and Promotion Network | Secretariat | Participate in meetings and internal communication of the Network. Keep Chair and WG informed | Regularly |
|  | All members of the WG | Take note of the updates given by the Network. Present an activity report on the Network to the BFUG | Regularly Second half of 2011 |
| Specific tasks as defined by the terms of references | Who? | How? | When? |
| - To cooperate with the Bologna Secretariat regarding the further development of the Bologna Website for a global audience; | All members of the WG | Feedback by e-mail to the Bologna Secretariat: - Suggestions on how to improve the existing website - News items, updates… | Regularly |
| - To support the Bologna Secretariat in convening a round table (with the participation of the European Commission and other main actors in higher education promotion in Europe) to devise a “road map” and to identify opportunities and actions for enhancing European-level promotion. | Small group composed of members of WG and IPN All members of the WG | To be linked to the progress of the EHEA Information & Promotion Network Prepare a proposal for convening the round table Provide feedback | Summer/autumn 2011 End of 2011 |
| - To provide information on policy dialogue events relevant to the Bologna Process, taking place in various frameworks and at various levels, through the Bologna Website & via e-mail to the BFUG. | All members of the WG | By e-mail to the Bologna Secretariat (e.g. short paragraphs on new developments/ events for the website or messages to be sent to the BFUG) | Regularly |
| - To support the host country Romania in preparing the Third Bologna Policy Forum with regard to both, the organisational aspects and the content – involving non-EHEA countries by way of electronic consultation (via the nominated contact persons). | All members of the WG | Feedback on the Second Bologna Policy Forum and proposals for follow-up Brainstorming in the WG regarding the format/ organisation and theme of the Third Bologna Policy Forum Input for detailed programme and content of the Third Bologna Policy Forum Evaluation | 27 May 2010 27 May 2010 28 October 2010 2011 May/June 2012 |

Timeline

| Date | Meetings | Action to be taken |
| --- | --- | --- |
| 27 May 2010 | WG meeting (Vienna) | - Feedback on and follow-up to 2nd BPF - First discussion on 3rd BPF - Agreement on updated ToR & work plan - Prepare update for BFUG |
| Mid-June 2010 | By e-mail | Written update, ToR and work plan to BFUG |
| 24-25 August 2010 | BFUG meeting (Alden Biesen) | Approval of updated ToR and work plan |
| 28 October 2010 | WG meeting (Bucharest) | - Discussion on format and organisation as well as theme of 3rd BPF - Feedback on EHEA website - Update on IPN - Concrete follow-up to BPF Statement |
| January 2011 (optional) | WG meeting (Vienna) | - Input for programme/ content of 3rd BPF - Update on IPN - Prepare update for BFUG - Concrete follow-up to BPF Statement |
| February 2011 | By e-mail | Written update to BFUG |
| 17-18 March 2011 | BFUG meeting (Hungary) |  |
| June 2011 | WG meeting (Bucharest, tbc) | - Update on IPN - Prepare final report for BFUG - Concrete follow-up to BPF Statement |
| September 2011 | By e-mail | Final report to BFUG |
| 13-14 October 2011 | BFUG meeting (Cracow) | Discussion / approval of final report |
| November 2011 (optional) | WG meeting (Bucharest, tbc) | - Update on IPN? - Reaction to BFUG discussion, if needed - Discussion on round table - Concrete follow-up to BPF Statement |
| January 2012 (tbc) & March 2012 (tbc) | BFUG meetings (Denmark) |  |
| 26-27 April 2012 | Ministerial Conference and 3rd BPF (Bucharest) |  |
| May / June 2012 | WG meeting (Bucharest, tbc) | - Evaluation of 3rd BPF and of WG - Possibly suggestions for next phase |