BFUG (HU/AD) 24_9b

BFUG Work Plan 2009-2012

CONTENTS

Introduction	2

Follow-up activities per priority area (for seminars etc. see the separate calendar of events)	5

Social dimension: equitable access and completion	5

Lifelong learning	5

Employability	6

Student-centred learning and the teaching mission of higher education	7

Education, research and innovation	7

International openness	7

Mobility	8

Data collection	9

Transparency tools	10

Funding	10

Continued actions	11

Quality Assurance	11

Independent Assessment	11

Annexes	12

# Introduction

In the Leuven/Louvain-la-Neuve Communiqué, the Ministers responsible for higher education in the countries participating in the Bologna Process identified the following higher education priorities for the coming decade:

- social dimension: equitable access and completion;

- lifelong learning;

- employability;

- student-centred learning and the teaching mission of higher education;

- education, research and innovation;

- international openness;

- mobility;

- data collection;

- multidimensional transparency tools;

- funding.

To implement the Bologna reforms and to make progress in all priority areas, strong efforts will be required especially at national and institutional level. However, these efforts can be supported by joint European action.

For the short term, the Ministers therefore entrusted the BFUG “to prepare a work plan up to 2012 to take forward the priorities identified in this Communiqué and the recommendations of the reports submitted to this Ministerial conference, allowing the future integration of the outcome of the independent assessment of the Bologna Process.

In particular the BFUG is asked:

- To define the indicators used for measuring and monitoring mobility and the social dimension in conjunction with the data collection;

- To consider how balanced mobility could be achieved within the EHEA;

- To monitor the development of the transparency mechanisms and to report back to the 2012 ministerial conference;

- To set up a network, making optimal use of existing structures, for better information on and promotion of the Bologna Process outside the EHEA;

- To follow-up on the recommendations of analysis of the national action plans on recognition”  (Leuven/Louvain-la-Neuve Communiqué, par. 26).

The present work plan agreed upon at the Stockholm and Brussels BFUG meetings is open to adjustments and additions after the 2010 Ministerial Conference in order to take into account the results of the independent assessment, the 2010 Focus Report and any new orientations that will be given by the Ministers.

The intention of the work plan is to list the actions that need to be taken jointly at European level to reach the goals set for each priority area. These European follow-up activities can take a variety of forms:

Working groups:

- To avoid the confusion that has resulted and inevitably would continue to result from the use of too many different terms (working group, coordination group, steering group, monitoring group, task force etc.), “BFUG working group” will be used as generic term for all kinds of groups established by the BFUG in order to fulfil a certain task within a set timeframe. The specific nature and the precise tasks of each group (e.g. coordination, monitoring, preparing a report) are outlined in the respective terms of reference.

- Working groups set up by the BFUG are in principle open to participation from all Bologna countries, the European Commission and the consultative members but also need to be of a workable size. As the groups work on behalf of the entire BFUG, their composition should reflect the diversity of the BFUG and the EHEA more generally. Where necessary, the groups can also decide to involve external experts.

- To keep the entire BFUG involved, the working groups will regularly report back to the BFUG. The final reports / conclusions for the 2009-2012 period should be presented and discussed no later than the BFUG meeting in October 2011.

Networks:

- Networks are meant to establish longer term cooperation between a large number of partners (potentially all countries and organisations participating in the Bologna Process).

- As issue networks, these networks connect experts in a specific field (e.g. student support or qualifications frameworks) from different countries and organisations and allow them to share information and examples of good practice, to assist each other, and possibly also to develop new policies.

Seminars/Conferences:

- In the early stages of the Bologna Process, a central function of the Bologna seminars was policy development. While international seminars and conferences can still play an important role in further policy development, the focus of the 2009-2012 period should be on communication and dissemination of the Bologna reforms.

- Rather than having a limited number of “official Bologna Seminars”, there therefore is an open calendar of events, encouraging countries and organisations to arrange as many seminars, conferences and workshops as possible.

- For an event to be included in the calendar of events that is published on the official Bologna website, it obviously has to be related to the Bologna Process and should be organised or at least supported by one of the countries or organisations participating in the Bologna Process. Moreover, it should in principle be open to participants from all Bologna countries, which however does not exclude international events that have a more regional focus.

- Invitations, presentations, reports and conclusions can be published on the website and forwarded to the BFUG on request of the organisers.

Discussions at BFUG meetings

- BFUG meetings can also be used to discuss a specific issue in more detail. For this purpose, delegates could volunteer to provide input for such a discussion. Alternatively, external experts could be invited to give a presentation.

Peer-learning activities

- Peer-learning activities organised across the EHEA can help to support the implementation and consolidation of the Bologna reforms.

- For this purpose, countries and organisations are encouraged to make known in which field they would like to receive assistance and/or in which fields they have expertise to offer. Individual BFUG members also have the opportunity to contact other BFUG members or the entire group by e-mail to exchange experience and to learn from each other.

- Last but not least, the BFUG might want to consider how to make better use of the Bologna website to foster peer-learning, to share expertise, to make publications known to a wider audience etc.

This list of possible follow-up activities at European level does not claim to be comprehensive and the BFUG is actively encouraged to develop additional forms of cooperation to take forward the different priority areas at European level.

Given that the largest part of the actions required to implement the Bologna reforms and to make progress in all priority areas will have to be taken at national and institutional level, an important task of the BFUG (and the working group “Reporting on the Implementation of the Bologna Process” in particular), will also be to find ways to get a good overview of what is actually going on at national and institutional level.

# Follow-up activities per priority area (for seminars etc. see the separate calendar of events)

| ## Social dimension: equitable access and completion |  |  |  |  |
| --- | --- | --- | --- | --- |
| Follow-up action | Chair(s) |  | Participants | Tasks |
| - Working group on social dimension | Spain, Ireland |  | Andorra, Austria, Belgium/Flemish Community, Croatia, Czech Republic, Estonia, France, Germany, Ireland, the Netherlands, Norway, Portugal, Slovenia, “the former Yugoslav Republic of Macedonia”, UK/EWNI, UK/Scotland, European Commission, BUSINESSEUROPE, ESU, EUA, EURASHE, Eurostat, Eurostudent | - See the terms of reference in annex 1 |
| - Peer-learning activities (seminars, workshops etc.) | e.g. working group on social dimension |  |  | - to test /disseminate the indicators, helping countries to set their measurable targets. - to exchange good practice on how to increase participation of underrepresented groups in higher education. |
| - Reporting on the implementation of the Bologna Process | See below (data collection, page 7) |  |  |  |
| ## Lifelong learning |  |  |  |  |
| Follow-up action |  | Chair(s) | Participants | Tasks |
| - Working group on qualifications frameworks |  | Council of Europe | Armenia, Austria, Belgium/Flemish Community, Belgium/French Community, Czech Republic, France, Germany, Ireland, Latvia, Malta, the Netherlands, Poland, Spain, Turkey, UK/Scotland, European Commission, ESU, EUA, EURASHE | - See the terms of reference in annex 2 |
| - Network of NQF correspondents |  | Council of Europe | NQF correspondents of all Bologna countries | - See the terms of reference in annex 9 - Exchange of experience in the elaboration of national qualifications frameworks and to facilitate self-certification of national qualifications frameworks by 2012 |
| - Recognition of Prior Learning European Network |  | UK / Scotland | Open to all Bologna countries and consultative members | - See the terms of reference in annex 10 |
| - Reporting on the implementation of the Bologna Process |  | See below (data collection, page 7) |  |  |
| ## Employability |  |  |  |  |
| Follow-up action |  | Chair(s) | Participants | Tasks |
| - Reporting on the implementation of the Bologna Process |  | See below (data collection, page 7) |  |  |
| ## Student-centred learning and the teaching mission of higher education |  |  |  |  |
| Follow-up action |  | Chair(s) | Participants | Tasks |
| - Reporting on the implementation of the Bologna Process |  | See below (data collection, page 7) |  |  |
| ## Education, research and innovation |  |  |  |  |
| Follow-up action |  | Chair(s) | Participants | Tasks |
| - Reporting on the implementation of the Bologna Process |  | See below (data collection, page 7) |  |  |
| ## International openness |  |  |  |  |
| Follow-up action |  | Chair(s) | Participants | Tasks |
| - Working group on the EHEA in a global context |  | Romania | Armenia, Austria, Belgium/Flemish Community, Belgium/French Community, Cyprus, France, Germany, Holy See, Hungary, Norway, Slovenia, Spain, UK, European Commission, Council of Europe, EI, ENQA, ESU, EUA, EURASHE, UNESCO, ACA, ENIC-NARIC networks, IAU | - See the updated terms of reference in annex 3 |
| - EHEA Information & Promotion Network |  | Austria, Belgium/Flemish Community, Estonia | Open to all 47 countries, European Commission, consultative members, ACA and EAIE | - See the terms of reference in annex 8 |
| ## Mobility |  |  |  |  |
| Follow-up action |  | Chair(s) | Participants | Tasks |
| - Working group on mobility |  | Germany | Armenia, Belgium/Flemish Community, Belgium/French Community, Croatia, Cyprus, Finland, France, Georgia, Hungary, Ireland, Italy, the Netherlands, Russia, Serbia, Slovenia, Spain, “the former Yugoslav Republic of Macedonia”, UK, European Commission, BUSINESSEUROPE, EI, ESU, EUA | - See the terms of reference in annex 4 |
| - Working group on recognition composed of BFUG members, ENIC-NARIC representatives and NQF correspondents |  | Latvia | Armenia, Austria, Belgium/Flemish Community, Belgium/French Community, Denmark, Estonia, Finland, France, Germany, Holy See, Ireland, Montenegro, the Netherlands, Serbia, UK/Scotland, European Commission, Council of Europe, ENQA, ESU, EUA, UNESCO | - See the terms of reference in annex 5 |
| - The Network of Experts on Student Support in Europe (NESSIE) |  | Austria, Denmark and Ireland | All countries and organisations participating in the Bologna Process are invited to join. | - to exchange information and - to assist each other in facilitating the portability of grants and loans. |
| - Reporting on the implementation of the Bologna Process |  | See below (data collection, page 7) |  |  |
| ## Data collection |  |  |  |  |
| Follow-up action |  | Chair(s) | Participants | Tasks |
| - Working group on reporting on the implementation of the Bologna Process |  | Latvia and Luxembourg | Armenia, Austria, Belgium/Flemish Community, Czech Republic, Finland, France, Germany, Montenegro, the Netherlands, Norway, Slovenia, Spain, Switzerland, Turkey, UK/Scotland, European Commission, EI, ENQA, ESU, EUA, EURASHE, Eurostat, Eurostudent, Eurydice [data collection in all 47 countries] | - See the terms of reference in annex 6 To assess the progress made with the implementation of each of the priority areas as well as the “old” action lines (e.g. quality assurance and recognition), stocktaking will be further refined and combined with the joint data collection efforts of Eurostat, Eurostudent, and Eurydice, which (except for Eurostudent) also cover all 47 Bologna countries. The aim is to produce one joint, comprehensive report on the implementation of the Bologna Process from a governmental perspective. In addition to that, EUA and ESU plan to continue their reporting from the points of view of higher education institutions and students. |
| ## Transparency tools |  |  |  |  |
| Follow-up action |  | Chair(s) | Participants | Tasks |
| - Working group on transparency tools |  | Belgium/Flemish Community | Armenia, Austria, Belgium/French Community, Croatia, Cyprus, Czech Republic, Denmark, Estonia, Finland, France, Germany, Italy, Malta, the Netherlands, Spain, Switzerland, UK/EWNI, European Commission, BUSINESSEUROPE, Council of Europe, EI, ENQA, ESU, EUA, EURASHE | - See the terms of reference in annex 7 |
| ## Funding |  |  |  |  |
| Follow-up action |  | Chair(s) | Participants | Tasks |
| - Reporting on the implementation of the Bologna Process |  | See above (data collection, page 7) |  |  |

# Continued actions

| ## Quality Assurance |  |  |  |
| --- | --- | --- | --- |
| Follow-up action | Chair(s) | Participants | Tasks |
| - E4 Group |  | ENQA, ESU, EUA, EURASHE | - To continue its cooperation in further developing the European dimension of quality assurance - To ensure that the European Quality Assurance Register is evaluated externally, taking into account the views of the stakeholders (par. 28). |
| - Reporting on the implementation of the Bologna Process | See above (data collection, page 7) |  |  |
| ## Independent Assessment |  |  |  |
| - The work on the independent assessment of the Bologna Process launched in the previous period was completed in spring 2010. |  |  |  |

# Annexes

Annex 1: Terms of reference

Name of the working group Social Dimension

Contact person (Chairs) Rafael Bonete (rbonete@usal.es) – Spain Brian Power (brian_power@education.gov.ie) - Ireland

Composition Andorra, Austria, Belgium/Flemish Community, Croatia, Czech Republic, Estonia, France, Germany, Ireland, the Netherlands, Norway, Portugal, Slovenia, “the former Yugoslav Republic of Macedonia”, UK/EWNI, UK/Scotland, European Commission, BUSINESSEUROPE, ESU, EUA, EURASHE, Eurostat, Eurostudent

Purpose and/or outcome (with a reference to paragraph 9 in the Leuven Communiqué) - To identify obstacles and how some countries have overcome these obstacles and analyze good practices put in place in some countries within the EHEA for reaching the goal that the student body entering, participating in and completing higher education at all levels reflects the diversity of the European population. - To analyze the actions taken in others parts of the educational system within the EHEA in order to increase the level of equity in Higher Education. - To analyze national/regional strategies at governmental level to widening access to Higher Education - To analyze good practices and national experiences in the field of elaborating core indicators used for measuring and monitoring the relevant aspects of the Social Dimension in higher education. - To analyze the responsibility of HEI taking into account the social (and thus employment) perspectives of their graduates. - To explore the feasibility of including the increasing relevance of social responsibility of HEIs in Europe (considering aspects related to innovation based regional and urban development in Europe and social engagements) in the concept of Social Dimension. - To explore the possibility of creating an European Observatory on Social Dimension of Higher Education (EOSDHE).

Reference to the Leuven/Louvain-la-Neuve Communiqué Paragraph 9, 21, 26.

Specific tasks - Collection of good practices in Social Dimension implementation in Higher Education at national and regional level. - Collection of measures taken in other parts of the educational system within the EHEA in order to increase the level of equity in Higher Education; - Collections of good practices and national experiences in defining core indicators used for measuring and monitoring the relevant aspects of Social Dimension in Higher Education; - To collect information of successful stories of improving employability due to the good practices of HEIs; - To encourage peer-learning activities (seminars, workshops etc.). - To discuss the pros and cons of elaborating a wider concept of social dimension for the near future.

Reporting Minutes of working group meetings or the results of online activities will be made available by the Bologna Secretariat. BFUG should also receive regular reports and updates. To allow for good communication with BFUG as a whole and for the necessary consultations, progress reports should be submitted at least two weeks before each BFUG meeting. In between BFUG meetings, updates can be circulated by the Bologna Secretariat via e-mail.

Meeting schedule 20 May 2010 First half of 2011 September 2011

Liaison with other action lines The chairs of the working group will participate in meetings of the working group on reporting on the implementation of the Bologna Process in order to liaise with stocktaking and data collection. Cooperation with other working groups, in particular those on mobility will be organized in the relevant context.

Annex 2: Terms of reference

Name of the working group Working Group on Qualifications Frameworks

Contact person (Chair) Sjur BERGAN – Council of Europe (Sjur.BERGAN@coe.int)

Composition Armenia, Austria, Belgium/Flemish Community, Belgium/French Community, Czech Republic, France, Germany, Ireland, Latvia, Malta, the Netherlands, Poland, Spain, Turkey, UK/Scotland, European Commission, CEDEFOP, ESU, EUA, EURASHE. EURYDICE is invited to participate in all discussions in the Working Group concerning reporting for the 2012 ministerial conference.

Purpose and/or outcome Continued coordination at the level of the EHEA and with the EQF-LLL to facilitate the implementation of the national qualifications frameworks and preparation for their self-certification against the overarching Qualifications Framework of the EHEA by 2012.

Reference to the Leuven/Louvain-la-Neuve Communiqué paragraph 12

Specific tasks - Consider and make recommendations on specific policy issues related to qualifications frameworks; - maintain and develop relations to the EQF-LLL, including contributing to the EQF Advisory Group; - organize, or stimulate the organization of, Bologna conferences and events on issues related to qualifications frameworks; - coordinate requests for assistance, including as regards self certification of national frameworks against the overarching framework of qualifications of the EHEA; - maintain and develop the Bologna QF web site (with input from the national correspondents); - assist in the preparation of meetings of the Network of national QF correspondents and follow up its work.

Reporting Minutes of working group meetings will be made available by the Bologna Secretariat. BFUG should also receive regular reports and updates. To allow for good communication with BFUG as a whole and for the necessary consultations, progress reports should be submitted at least two weeks before each BFUG meeting. In between BFUG meetings, updates can be circulated by the Bologna Secretariat via e-mail. The final report / conclusions will be presented and discussed no later than the BFUG meeting in the second half of 2011.

Meeting schedule First meeting: Strasbourg, 10 November 2009 Second meeting: Bruxelles, 16 February 2010 Third meeting: Bruxelles, 11 June 2010 Fourth meeting: Strasbourg, 27 October 2010 Fifth meeting: Budapest, 27 May 2011 Further meetings to be decided

Liaison with other action lines Recognition (via the chair of the WG who is also a member of the QF WG) International openness Reporting on the implementation of the Bologna Process

Additional remarks

Annex 3: Updated terms of reference

Name of the working group International Openness: The European Higher Education Area in a Global Context

Contact person (Chair) Luminița NICOLESCU – Romania (luminicolescu@yahoo.com)

Composition Armenia, Austria, Belgium/Flemish Community, Belgium/French Community, Cyprus, France, Germany, Holy See, Hungary, Norway, Slovenia, Spain, UK, European Commission, Council of Europe, EI, ENQA, ESU, EUA, EURASHE, UNESCO, ACA, ENIC-NARIC networks, IAU

Purpose and/or outcome - To take forward the recommendations of “The European Higher Education Area (EHEA) in a global context: Report on overall developments at the European, national and institutional levels”. - To support the preparations of the 2010 Bologna Policy Forum.  - To support the follow-up to the 2010 Bologna Policy Forum and the preparations of the 2012 Third Bologna Policy Forum - To set up a network, making optimal use of existing structures, for better information on and promotion of the Bologna Process outside the EHEA.  - To monitor the development of the EHEA Information and Promotion Network If needed, the mandate of the group for the period until 2012 will be adjusted in line with the decisions taken by the Ministers in Budapest and Vienna in March 2010. 

Reference to the Leuven/Louvain-la-Neuve Communiqué Paragraphs 16 and 26. Additional reference: Vienna Bologna Policy Forum Statement

Specific tasks - To cooperate with the Bologna Secretariat regarding the further development of the Bologna Website for a global audience; - To set up a pool of experts across the EHEA countries in order to support the Bologna Secretariat in facilitating coordinated information visits to and from non-EHEA countries;  [compromise between pool of experts and ad-hoc arrangement agreed by Madrid BFUG] - To facilitate a first meeting of the network for better information on and promotion of the Bologna Process outside the EHEA;  - To support the Bologna Secretariat in convening a round table (with the participation of the European Commission and other main actors in higher education promotion in Europe) to devise a “road map” and to identify opportunities and actions for enhancing European-level promotion. - To provide information on policy dialogue events relevant to the Bologna Process, taking place in various frameworks and at various levels, through the Bologna Website. - To support the host countries Hungary and Austria in preparing the Second Bologna Policy Forum with regard to both the organisational aspects and the content – involving the non-EHEA countries that participated in the First Bologna Policy Forum by way of electronic consultation.  - To support the host country Romania in preparing the Third Bologna Policy Forum with regard to both, the organisational aspects and the content – involving non-EHEA countries that nominated a contact person for the follow-up to the Second Bologna Policy Forum by way of electronic consultation.

Reporting Minutes of working group meetings will be made available by the Bologna Secretariat. BFUG should also receive regular reports and updates. To allow for good communication with BFUG as a whole and for the necessary consultations, progress reports should be submitted at least two weeks before each BFUG meeting. In between BFUG meetings, updates can be circulated by the Bologna Secretariat via e-mail. The final report / conclusions will be presented and discussed no later than the BFUG meeting in the second half of 2011.

Meeting schedule First meeting: Vienna, 28 October 2009 Second meeting: Vienna, 25 January 2010 Third meeting: Vienna, 27 May 2010 (to set up a detailed work plan for the period 2010-2012 to be presented to the BFUG meeting in August 2010, taking into account the results of the Budapest/Vienna Ministerial Meeting) Fourth meeting: Bucharest, 28 October 2010 Fifth meeting: Vienna, 18 January 2011 Sixth meeting: Brussels, 19 May 2011 Seventh meeting: Bucharest, 9 November 2011 Eight meeting: May / June 2012 (evaluation of the third BPF) (if necessary, some meetings can be coupled with other Bologna events taking place at other locations)

Liaison with other action lines Cooperation with the working group “Reporting on the implementation of the Bologna Process” will be organised with the chairs of that group so that it meets the needs of both groups. Cooperation with other elements of the work programme will be sought where appropriate.

Additional remarks

Annex 4: Terms of reference

Name of the working group Working Group on Mobility

Contact person (Chair) Peter GREISLER – Germany (peter.greisler@bmbf.bund.de)

Composition Armenia, Belgium/Flemish Community, Belgium/French Community, Croatia, Cyprus, Finland, France, Georgia, Hungary, Ireland, Italy, the Netherlands, Russia, Serbia, Slovenia, Spain, “the former Yugoslav Republic of Macedonia”, UK, European Commission, BUSINESSEUROPE, EI, ESU, EUA

Purpose and/or outcome - To contribute to the discussions in the working group “Reporting on the Implementation of the Bologna Process” on development of a precise definition of the benchmark mentioned in the Leuven/Louvain-la-Neuve Communiqué - To identify problems related to the balance of incoming and outgoing students and identify examples of good practice - To assess the structural, legal, financial and other obstacles to mobility of students and staff and to identify possibilities for action for Ministers and stakeholders in order to improve mobility - To draft an EHEA Strategy for mobility, for adoption by Ministers in 2012, based on the collection of good practice on mobility and with the purpose of stimulating further efforts in the area of mobility.

Reference to the Leuven/Louvain-la-Neuve Communiqué Paragraphs 18-21, 26.

Specific tasks - To contribute to the definition of the benchmark that “in 2020, at least 20% of those graduating in the Higher Education Area should have a study or training period abroad” - To define the needs of improved and enhanced data collection with regard to information on the reasons for mobility (studies, work experience, language course, etc), the length of the stay, the types of mobility (free mover, programme mobility, vertical mobility), mobility by cycle, by socio-economic background and to communicate the results to the working group Implementation of the Bologna Process - To collect specific examples of different kinds of mobility barriers for students and staff (structural, legal, financial, other) – possibly in co-operation with the working groups on social dimension and recognition - To identify examples of good practice to overcome mobility barriers and develop recommendations on actions to be taken on different levels - To identify reasons for imbalanced mobility and collect examples of good practice for encouraging balanced mobility - To liaise with relevant mobility seminars organised in the 2009-2012 period - Based on discussions with BFUG on possible actions, to draft an EHEA Strategy for Mobility

Reporting Minutes of working group meetings will be made available by the Bologna Secretariat. BFUG should also receive regular reports and updates. To allow for good communication with BFUG as a whole and for the necessary consultations, progress reports should be submitted at least two weeks before each BFUG meeting. In between BFUG meetings, updates can be circulated by the Bologna Secretariat via e-mail. The draft of the EHEA Strategy for mobility will be presented and discussed no later than the BFUG meeting in the second half of 2011.

Meeting schedule First meeting: Berlin, 13 January 2010 Second meeting: Berlin, 12 May 2010 Third meeting: Budapest, 4 November 2010 Fourth meeting: Berlin, 29-30 March 2011

Liaison with other action lines The chair of the working group will participate in meetings of the working group on reporting on the implementation of the Bologna Process in order to liaise with stocktaking and data collection. Cooperation with other working groups, in particular those on social dimension, the EHEA in a global context, and recognition will be organized in the relevant context.

Additional remarks

Annex 5: Terms of reference

Name of the working group Working Group on Recognition

Contact person (Chair) Andrejs Rauhvargers – Latvia (andrejs.rauhvargers@lu.lv)

Composition Armenia, Austria, Belgium/Flemish Community, Belgium/French Community, Denmark, Estonia, Finland, France, Germany, Holy See, Ireland, Montenegro, the Netherlands, Serbia, UK/Scotland, European Commission, Council of Europe, ENQA , ESU, EUA, UNESCO

Purpose and/or outcome To follow-up on the recommendations of analysis of the national action plans on recognition with a view to make recognition of qualifications and credits more coherent across the EHEA and improve recognition with other parts of the world Make recommendations on how member countries, the Networks and the BFUG could define policies to implement the recommendations of the study

References to the Leuven/Louvain-la-Neuve Communiqué Paragraphs 26, 6, 11, 19, 22.

Specific tasks Following up on the recommendations of analysis of the national action plans on recognition - Make recommendations on the respective roles and responsibilities of public authorities responsible for overall higher education policy, higher education institutions, national information centres on recognition and other competent recognition authorities in developing national policies to implement the recommendations of the analysis; - Make recommendations on considerations countries should include in reviewing their recognition legislation, taking account of the LRC and the policies and objectives of the EHEA; - Clarify differences in recognition criteria and procedures among countries of the EHEA and make recommendations with a view to ensuring more equal treatment of applications for recognition throughout the EHEA, with reference to academic as well as de jure and de facto professional recognition; - Explore possible ways to include an assessment of the quality of the internal recognition procedures of HEIs in the internal quality procedures as well as external quality reviews of HEIs; - Associate the Working Group on qualifications frameworks in any consideration of the role of QFs in implementing the recommendations of the analysis.

Reporting Minutes of working group meetings will be made available by the Bologna Secretariat. BFUG should also receive regular reports and updates. To allow for good communication with BFUG as a whole and for the necessary consultations, progress reports should be submitted at least two weeks before each BFUG meeting. In between BFUG meetings, updates can be circulated by the Bologna Secretariat via e-mail. The final report / conclusions will be presented and discussed no later than the BFUG meeting in the second half of 2011.

Meeting schedule First meeting: Brussels, 16 February 2010 Second meeting: Brussels, 10 June 2010 Third meeting: Strasbourg, 25 October 2010 Fourth meeting: Riga, 27 April 2011

Annex 6: Terms of reference

Name of the working group Reporting on the Implementation of the Bologna Process

Contact persons (Chairs) Germain Dondelinger - Luxembourg (germain.dondelinger@mesr.etat.lu) Andrejs Rauhvargers - Latvia (andrejs.rauhvargers@lu.lv)

Composition Armenia, Austria, Belgium/Flemish Community, Czech Republic, Finland, France, Germany, Montenegro, the Netherlands, Norway, Slovenia, Spain, Switzerland, Turkey, UK/Scotland, European Commission, EI, ENQA, ESU, EUA, EURASHE, Eurostat, Eurostudent, Eurydice

Purpose and/or outcome To further refine the evidence-based stocktaking methodology: - to provide reliable, comparable data and to take stock of progress towards realising the European Higher Education Area; - to make progress in the construction of a structured and standardised monitoring system consisting of indicators and qualitative analysis - to allow for comparisons to be made between countries and to allow for monitoring changes over time within countries as well as between countries; To prepare an overall report on the implementation of the Bologna Process for 2012, integrating data collected by Eurostat/Eurostudent and Eurydice.

References to the Leuven/Louvain-la-Neuve Communiqué Paragraphs 18, 21, 26 & 27.

Specific tasks - To identify the key issues to be covered by the report and the way in which they should be addressed (quantifiable indicators or qualitative analysis); - to specify the indicators to measure progress; - to identify the data required; - to define the template /questionnaire to collect information from the Bologna countries in the view of qualitative analysis; - to analyse and contextualise the data from various sources; - to identify the most appropriate ways of presenting the different results (the “traffic lights” of stocktaking, maps, graphs, analytical text etc.) - to assist Eurydice in drafting the overall report for approval by the BFUG in advance of the 2012 ministerial conference. - To develop a precise definition of the 20% mobility benchmark.

Reporting Minutes of working group meetings will be made available by the Bologna Secretariat. BFUG should also receive regular reports and updates. To allow for good communication with BFUG as a whole and for the necessary consultations, progress reports should be submitted at least two weeks before each BFUG meeting. In between BFUG meetings, updates can be circulated by the Bologna Secretariat via e-mail. A concrete proposal on the overall reporting, including the indicators, will be submitted to the BFUG for its meeting in Alden Biesen on 24-25 August 2010. The final report will be presented and discussed at the BFUG meeting in January 2012.

Meeting schedule First meeting: Luxembourg, 4 November 2009 Second meeting: Luxembourg, 21 January 2010 Third meeting: Riga, 16 June 2010 Fourth meeting: Luxembourg, 16 November 2010 Fifth meeting: beginning of July (tbc)

Additional remarks

Annex 7: Terms of reference

Name of the Working Group Transparency Tools

Contact person (Chair) Noël Vercruysse (noel.vercruysse@ond.vlaanderen.be) – Belgium/Flemish Community

Composition: Armenia, Austria, Belgium/French Community, Croatia, Cyprus, Czech Republic, Denmark, Estonia, Finland, France, Germany, Italy, Netherlands, Spain, Switzerland, UK/EWNI, European Commission, BUSINESSEUROPE, Council of Europe, EI, ENQA, ESU, EUA, EURASHE.

Purpose and outcomes - to monitor the development of the transparency tools and mechanisms both the purposes and the objectives (information, accountability, quality) and the indicators and criteria used (input/processes, output/outcome); - to make a report to the 2012 ministerial conference.

Reference to the Leuven/Louvain-la-Neuve Communiqué Paragraphs 26, point 3

Specific tasks To organize a seminar on transparency tools open for the participation of the BFUG. To prepare a report for the 2012 ministerial conference.

Reporting Minutes of the meetings of working group will be made available to the BFUG. BFUG will receive regular reports and updates as well as a working plan and draft intermediate reports for written consultation and comments. The final report / conclusions will be presented and discussed no later than the BFUG meeting in the second half of 2011.

Meeting Schedule First meeting: Brussels, 30 November 2009 To the 2012 ministerial conference - 5 meetings: 1 in 2010, 3 WG meetings, one workshop and one seminar for the BFUG in 2011. The last 2011 meeting can be postponed for early 2012.

Liaison with other action lines There is a clear interaction with the working group “Reporting on the implementation of the Bologna Process”, in particular concerning data collection and the definition of indicators used for the monitoring and measuring mobility and the social dimension.

Additional remark The communiqué of the 2009 world conference on higher education mentions also the need for greater information, openness and transparency regarding different missions and performances of individual institutions.

Annex 8: Terms of reference

EHEA Information and Promotion Network

Contact persons (Chairs) Three co-chairs to be elected among the members of the network, taking into account geographical diversity and different levels of expertise/different traditions in higher education promotion. 2010-2012: Austria, Belgium/Flemish Community, Estonia

Composition - Open to all 47 countries, European Commission and consultative members, representatives nominated by the respective BFUG members - Bologna Secretariat - Academic Cooperation Association (ACA) - European Association of International Education (EAIE)

Purpose and/or outcome - Provision of clear and consistent information on the Bologna Process and the European Higher Education Area (EHEA) in countries outside the EHEA. - Enhancing the international promotion of the European Higher Education Area. - Putting the promotion of national higher education systems in a European context.

Reference to the Leuven/Louvain-la-Neuve Communiqué Paragraph 26: “BFUG is asked […] To set up a network, making optimal use of existing structures, for better information on and promotion of the Bologna Process outside the EHEA”;

Specific tasks - Develop an overview of existing initiatives/activities by all members of the network in the field of promotion of national higher education systems & the EHEA (state of the art); - Support the Bologna Secretariat and the Working group “International Openness: European Higher Education in a Global Context” regarding the further development of specific information material (to be used e.g. at international fairs and visits) and of the EHEA Website for a global audience. - Design measures to enhance the promotion of the EHEA and of national higher education systems as part of the EHEA. - Foster the exchange of good practice and know-how as well as peer learning in the field of national-level promotion of higher education in a European context. - Advise/support the Working Group “International Openness: European Higher Education in a Global Context” in convening a round table (with the participation of the European Commission and other main actors in higher education promotion in Europe) to devise a “road map” and to identify opportunities and actions for enhancing European-level promotion.

Reporting Minutes of the Network will be made available to the BFUG and its Working Group “International Openness: European Higher Education in a Global Context”. Regular updates should be given to the Working Group “International Openness: European higher education in a Global Context”. An activity report will be presented to the BFUG via its Working Group “International Openness: European Higher Education in a Global Context” in the second half of 2011.

Meeting schedule First meeting: Vienna, 28 May 2010 Second meeting: Bonn, 17 December 2010 Third meeting: Vienna, 17 January 2011 Fourth meeting: Brussels, 11 March 2011

Liaison with other action lines

Additional remarks Organisation of work: The current terms of reference might be re-examined after the Bucharest ministerial conference in April 2012. Any new specific activity to be developed beyond the current terms of reference should be agreed upon by the BFUG, on the basis of proposals to be made by the Working Group “International Openness: European Higher Education in a Global Context”.

Annex 9: Terms of reference

Network of National Correspondents on Qualifications Frameworks

Contact person (Chair) Sjur BERGAN (Sjur.BERGAN@coe.int)

Composition - All countries of the EHEA are invited to appoint one or more members of the Network. Members should have responsibilities as concerns the development and implementation of the national qualifications framework in their home countries. In cases where countries develop comprehensive frameworks, the responsibilities of the national correspondent(s) should include the higher education part of the national framework. - The European Commission and CEDEFOP are invited to participate in the plenary meetings of the Network with specific reference to their responsibility for the implementation of the European Qualifications Framework for lifelong learning (EQF) and the follow-up of developments of national qualifications framework for lifelong learning. - Consultative members of the BFUG as well as the European Training Foundation are also invited to the plenary meetings of the Network. - The Chair may invite individual experts or organizations to participate in meetings of the Network on an ad hoc basis and with specific reference to their role in relation to one or more items of the agenda of that meeting.

Purpose and/or outcome The Network should facilitate the sharing of experience in the development of national qualifications frameworks compatible with the overarching framework of qualifications of the EHEA (QF-EHEA) as well as with the EQF. It should provide a forum for national correspondents to exchange experience and to discuss issues of particular relevance to the development and implementation of national frameworks. The Network should seek further cooperation with the National Coordination Points (NCPs) of the EQF.

Reference to the Leuven/Louvain-la-Neuve Communiqué paragraph 12

Specific tasks - further contacts and cooperation between national correspondents of member countries; - further the exchange of experience and provide a platform for discussion of issues of particular relevance to the development and implementation of national frameworks compatible with the QF-EHEA; - as required, offer advice on the development and implementation of national frameworks compatible with the QF-EHEA; - further and stimulate cooperation with the EQF-LLL, in particular with its National Coordination Points; - exchange experience with and provide mutual support for the self certification of national qualifications frameworks; - stimulate the organization of, Bologna conferences and events on issues related to qualifications frameworks; - as required, advice the Bologna Working Group on Qualifications Frameworks.

Reporting Minutes of working group meetings will be made available to BFUG on the protected part of the website (by the Bologna Secretariat). BFUG should also receive regular reports and updates. To allow for good communication with BFUG as a whole and for the necessary consultations, progress reports should be submitted at least two weeks before each BFUG meeting. In between BFUG meetings, updates can be circulated by the Bologna Secretariat via e-mail. A section on the Network of national correspondents should be included in the report by the Working Group on Qualifications Frameworks, which will be presented to the BFUG meeting in October 2011.

Meeting schedule Strasbourg, 25 March 2011 Autumn 2011, jointly with the National Coordination Points of the EQF (time and place tbc) Further meetings to be decided

Liaison with other action lines Recognition International openness Reporting on the implementation of the Bologna Process

Additional remarks Except in exceptional circumstances, members and observers shall cover the cost of their own participation.

Annex 10: Terms of reference

Recognition of Prior Learning European Network

Contact persons (Chair) Heather GIBSON (h.gibson@qaa.ac.uk)

Composition We would invite expressions of interest from all Bologna countries and consultative members and are interested in particular in practitioner representatives who can discuss their work on RPL or who are interested to develop its use.

Purpose and/or outcome - To help promote and inform the effective use and practice of RPL across participating countries - To provide a means for member countries to share and learn from policies and practice across Europe in relation to RPL development - To build links between European countries at various stages in RPL development.

References to the Leuven/Louvain-la-Neuve Communiqué Paragraphs 9, 10, 11, 13.

Specific tasks - To link with other countries developing RPL - To allow educators, practitioners and policy-makers working in RPL to share practice and inform progress - To share and explore ways in which RPL can best support student- centred learning, flexible learning paths, lifelong learning, and widening participation agendas across the Bologna process - To share and explore ways in which RPL can help support issues such as employer engagement and workforce development in Bologna - To establish and build upon an evidence base of RPL practice from across Bologna countries, and consider how cross-border RPL might be fostered - To consider the conclusions and recommendations from the 2010 RPL seminar (see below) and how these might best be taken forward. The full seminar report is available on the Bologna website - To liaise with other relevant networks and working groups, in particular the BFUG Working Groups on Recognition and National Qualifications.

Reporting To BFUG by minutes of working group meetings being made available through the Bologna Secretariat.

Meeting schedule First meeting: Glasgow, 5 November 2010 Second meeting: Glasgow, 23 June 2011

Background information: conclusions and recommendations from the 2010 RPL seminar General - While there is a good deal of RPL practice, it remains too concentrated in a small number of systems and HEIs and even where it is most established, it is not developed across the whole sector - There is no uniform approach or single model of RPL which fits all qualifications or situations. There are however some generic tools which can help and which can be adapted for different contexts - RPL can help with and should be considered in the context of, skills, employability and equality/widening participation agendas - The national context seems to be crucial in providing a policy drive or impetus for the development of RPL. This is clear from the Irish and Scottish contexts in particular, but also in the context of the Netherlands. Although the French situation was not represented, it is the case that in France, it is possible to award degrees entirely on the basis of RPL, a development which was driven by national policy concerns and context - It is important to achieve a good balance, between regulations/guidelines and institutional autonomy, between generic and discipline-specific practices and between national and European infrastructure and contexts - RPL fits with and needs the other elements of the EHEA infrastructure and recognition 'tools' - The learning outcomes approach and the use of national qualifications frameworks are helpful to institutions both in driving and enabling efficient and effective approaches to RPL – indeed ESU argued that they are pre-requisites Lifelong learning, widening participation, wider access - RPL can break down barriers and expand horizons of learners and institutions alike Flexible learning paths - RPL is a useful tool in helping to develop more flexible and varied learning paths, as evidenced by several projects presented at the seminar. Engagement with employers and workforce development - RPL can lead to greater efficiency (workers spend less time out of workforce) and greater effectiveness (c.f. Scottish Police College initiative) - Dialogue with stakeholders, including learners and employer/professional bodies can play a crucial role in the development of and the acceptance of RPL RPL processes and procedures – designing RPL programmes and innovative developments - It is important for higher education institutions to have RPL policies and procedures which are transparent and consistent - Streamlined and more diverse procedures for RPL are helpful both for widening its application and can be beneficial in terms of improving professional practice of teachers and knowledge and learning strategies of learners. - If RPL is to become more widely practiced and to be more widely accepted, it will be important to emphasise and demonstrate that the same standards and equally robust quality assurance arrangements exist for RPL as exist for traditional undergraduate and graduate provision Dialogue with stakeholders, including learners and employer/professional bodies can play a crucial role in the development of and the acceptance of RPL Student experiences of RPL across Bologna countries - Concerns expressed at the lack of penetration of RPL within the EHEA in plenary were reinforced by student representatives, who reported that the perceptions of students indicated that the practice of RPL was limited to a small number of countries, In this context, the importance of engaging students in dialogue regarding the development and use of RPL at all levels, was endorsed. Building assessment capacity and capability for RPL - Given the current mismatch between policy and practice, between lofty ambitions and the current reality, it might be helpful for the next two years to concentrate on 'big wins' to ramp up capacity and thereby awareness and demand Proposed RPL Network - It would be helpful to have an agreed definition of what is meant by RPL in the context of the proposed network, and for that definition to be inclusive - It would be helpful if the scope and purposes of RPL could be articulated in such a way as to bring together skills, employability, lifelong learning and quality agendas - There was broad support from participants for the proposed European RPL network and that it should, at least initially, be led by Scotland, Ireland and the Netherlands. - It was agreed that there was a need to share and disseminate more widely existing experience of RPL processes and practice, but also further to undertake research into the use and impact of RPL. - It was agreed that there should be some scoping of the role of the network, particularly including learners, but also considering whether or not the network would focus on HE only, or would also cover other aspects of RPL developments, such as the EQF for lifelong learning. Areas of activity which could be tested in the scoping exercise might include: Capacity building; the role of NQFs in supporting RPL in different contexts; collaborative partnerships; impact of RPL on learner; impact on HEIs/pedagogy/assessment; impact on workplace; role of RPL in supporting mobility/transitions between different learning contexts. Recommendation to the Bologna Follow Up Group That BFUG agrees the establishment of a European RPL network for sharing and developing practice in RPL and to advise the BFUG as required and that the network should, at least initially, be led by Scotland, Ireland and the Netherlands. Recommendation to higher education institutions and national rectors conferences That HEIs and NRCs incorporate RPL within the development of their approaches to lifelong learning and specifically within their implementation of the European Universities' Charter on Lifelong Learning. That HEIs and NRCs involve student representatives in the development of their RPL processes and procedures. Recommendation to quality agencies That national and European quality agencies incorporate appropriate reference to RPL procedures and processes within their own guidelines, procedures and regulations.