BFUG (HU/AD) 24_9.2b

Mobility Work plan 2010 -2012

updated 21 February 2011

| Date | Action | Content |
| --- | --- | --- |
| 13 January 2010 | WG Meeting Berlin | - 20% benchmark - data issues - agree on work plan |
| 12 May 2010 | WG Meeting Berlin | - If necessary, review work plan after Budapest/Vienna conference - Discuss elements of mobility strategy - Agree on survey to be sent out to BFUG members on mobility obstacles, good practice examples for increasing mobility and for encouraging a balanced flow of mobility (together with reporting group/as a separate exercise?) |
| 30 September 2010 | Deadline for country replies to mobility questionnaire |  |
| 4 November 2010 | WG Meeting Budapest | - Discussion on results of questionnaire and ACA mobility data - Develop recommendations |
| 31 January 2011 | First draft of mobility strategy to be sent to WG members |  |
| 21 February 2011 | Comments by WG members |  |
| 14 March 2011 | Second draft of mobility strategy to be sent to WG members |  |
| 17-18 March 2011 | BFUG meeting Budapest |  |
| 28-29 March 2011 | DAAD Seminar “From Imbalanced to Balanced Mobility in the EHEA – Current Challenges and Perspectives for the Future” |  |
| 29-30 March 2011 | WG Meeting Berlin | - Discuss draft of mobility strategy - Discuss input from DAAD seminar and other mobility seminars |
| June 2011 (date tbc) | WG Meeting | - Agree on EHEA Mobility Strategy |
| 13-14 October 2011 | BFUG Meeting | - Presentation of Draft EHEA Mobility Strategy |
| 26-27 April 2012 | Ministerial Conference Bucharest | - Endorsement/Adoption of EHEA Mobility Strategy |