BFUG (AD/HU) 24_9.8c

BFUG Working Group

“Multidimensional transparency tools”

“Towards a transparent landscape of European Higher Education”

DRAFT Work Plan 2009-2012

Leuven-Louvain-la-Neuve Communiqué: The BFUG is asked to monitor the development of the transparency mechanisms and to report back to the 2012 ministerial conference.

| Tasks | Who? | How? | When? |  |
| --- | --- | --- | --- | --- |
| - To agree on the scope of the working group on multidimensional transparency tools and to define the linkages with other issues as there are: quality, accountability,… | WG | Meeting | Meeting of November 30th 2009 |  |
| - Preparation of a questionnaire on relevant developments in Member states on transparency for the meeting of the Directors-General for Higher Education 13-14 September 2010, in Namur | Preparation and Draft : Chair and Bologna secretariat Comments: Working Group | Draft by the Chair and the Bologna Secretariat; Written contribution by the working group. | The 1st draft of questionnaire will be prepared by the end of April. The WG will be asked to comment on it in form of written contributions by mid May. |  |
| - To take stock of and discuss presentations and outcomes of the DG HE meeting complemented with new developments in the field of ranking in higher education. - Eventual invitation of and discussion with international experts – originally planned to invite to the mini seminar – who would comment on outcomes of the DGHE meeting and on new developments. (still to be discussed and agreed on by the WG per email) - Discussion of the organisation of the mini seminar | WG | Meeting | Meeting WG 11 October 2010 |  |
| - To agree on a conceptual definition of transparency tools and on the structure of the report | Preparation and Draft : Chair and Bologna secretariat Comments and endorsement: Working Group | Meeting Workshop with invited experts | WG Meeting April 2011 Workshop June 2011 |  |
| - To analyse the existing transparency tools according their scope, their relevance, their rationale, their purposes and objectives, their perspective, their dimensions, their indicators, etc. eventually in the frame of a mini seminar. | WG | Meeting | WG Meetings September/December 2011 |  |
| - Organization of a mini seminar for the entire BFUG | Chair and Bologna secretariat | Draft by the Chair and the Bologna Secretariat; Written contribution by the working group. Organizational arrangements with the hosts | November 2011 |  |
| - To prepare a report on the development of transparency mechanisms to the BFUG and to the 2012 ministerial conference | WG | Meeting | Meeting WG December 2011 or January 2012 |  |