- Roadmap for Drafting the Bucharest Ministerial Communiqué

| No. | Bucharest Communiqué Drafting Phase | When? | Who? |
| --- | --- | --- | --- |
|  | Adoption of the roadmap for drafting the Bucharest Ministerial Communiqué | Yerevan BFUG Board meeting 7 September 2011 | BFUG Board |
|  | Circulating to the BFUG members a draft document outlining the main issues and thematic areas to be included in the Bucharest Communiqué | 1 October 2011 | BFUG Secretariat, under the coordination of the Polish and Armenian BFUG Chairs and the Romanian Vice-Chair |
|  | Discussing the main issues and thematic areas to be included in the Bucharest Communiqué according to the recommendations contained within the reports of the BFUG WGs/ Networks | Cracow BFUG meeting 13-14 October 2011 | BFUG |
|  | Draft 0 of the Bucharest Communiqué | Copenhagen BFUG Board meeting 30 November 2011 | BFUG Secretariat, under the coordination of the Polish and Armenian / Danish and Azerbaijani BFUG Chairs and Romanian Vice-Chair |
|  | Redrafting the communiqué according to the comments of the BFUG Board | 30 November - 18 December 2011 | BFUG Secretariat, under the coordination of the Polish and Armenian / Danish and Azerbaijani BFUG Chairs and Romanian Vice-Chair |
|  | Circulating Draft 1 of the communiqué to the BFUG members for their feedback (with a deadline: Wednesday, 4 January 2012) | 19 December 2011 | BFUG Secretariat |
|  | Redrafting the communiqué according to the BFUG members’ comments | 4-10 January 2012 | BFUG Secretariat, under the coordination of the Danish and Azerbaijani BFUG Chairs and Romanian Vice-Chair |
|  | Discussing draft 2 of the Bucharest Communiqué | Copenhagen BFUG meeting (I) 18-19 January 2012 | BFUG |
|  | Integrating feedback received during the Copenhagen BFUG meeting and possibly the results of the Reporting on the Bologna Process implementation exercise | 20 January 2012 – 31 January 2012 | BFUG Secretariat |
|  | Circulation to the BFUG of draft 3 of the Bucharest Communiqué | 1 February 2012 | BFUG Secretariat |
|  | Discussing draft 3 of the Bucharest Communiqué | BFUG Board in Azerbaijan (February 2012 – date tbc) | BFUG Board |
|  | Integrating feedback received during the Azerbaijan BFUG Board meeting | End of February 2012 | BFUG Secretariat, under the coordination of the Danish and Azerbaijani BFUG Chairs and Romanian Vice-Chair |
|  | Circulation of draft 4 of the Bucharest Communiqué to the BFUG | 1 March 2012 | BFUG Secretariat |
|  | Receiving final comments from BFUG members | 8 March 2012 | BFUG Secretariat |
|  | Integrating the feedback received from BFUG members | 8-11 March 2012 | BFUG Secretariat, under the coordination of the Danish and Azerbaijani BFUG Chairs and Romanian Vice-Chair |
|  | Circulating draft 5 of the Bucharest Communiqué to the BFUG members | 12 March 2012 | BFUG Secretariat |
|  | Discussing draft 5 of the Bucharest Communiqué and the adoption by the BFUG of the FINAL VERSION to be submitted to EHEA Ministers for adoption on April 26-27 | Copenhagen BFUG meeting (II) 21-22 March 2012 | BFUG |
|  | Circulation of the BFUG endorsed draft of the Bucharest Ministerial Communiqué | 25 March 2012 | Bologna Secretariat |
|  | Ministerial adoption of the Bucharest Communiqué | Bucharest Ministerial Conference 26-27 April 2012 | EHEA ministers |