- Roadmap for Drafting the Bucharest Ministerial Communiqué

- Version 3/14.10.2011

| No. | Bucharest Communiqué Drafting Phase | When? | Who? |
| --- | --- | --- | --- |
|  | Circulating to the BFUG members a draft document outlining the main issues and thematic areas to be included in the Bucharest Communiqué | 3 October 2011 | BFUG Secretariat, under the coordination of the Polish and Armenian BFUG Chairs and the Romanian Vice-Chair |
|  | Circulating Draft 1 of the Bucharest Communiqué to the BFUG members for their feedback | 12 December 2011 | BFUG Secretariat |
|  | Deadline for receiving written comments on Draft 1 of the Bucharest Communiqué from the BFUG members | 4 January 2011 | BFUG members |
|  | Redrafting the Communiqué according to the BFUG members’ comments | 4-10 January 2012 | BFUG Secretariat, under the coordination of the Danish and Azerbaijani BFUG Chairs and the Romanian Vice-Chair |
|  | Circulating Draft 2 of the Bucharest Communiqué to the BFUG members | 10 January 2012 | BFUG Secretariat |
|  | Discussing Draft 2 of the Bucharest Communiqué | Copenhagen BFUG meeting (I) 18-19 January 2012 | BFUG members |
|  | Deadline for receiving written comments from the BFUG members | 1 February 2012 | BFUG members |
|  | Redrafting the Communiqué according to the feedback from the BFUG members | 1-22 February 2012 | BFUG Secretariat, under the coordination of the Danish and Azerbaijani BFUG Chairs/ Romanian Vice-Chair, in consultation with the BFUG Board |
|  | Circulation of Draft 3 of the Bucharest Communiqué to the BFUG members | 5 March 2012 | BFUG Secretariat |
|  | Discussing Draft 3 of the Bucharest Communiqué and adoption by the BFUG of the FINAL VERSION for EHEA Ministerial adoption on April 26-27 | Copenhagen BFUG meeting (II) 19-20 March 2012 | BFUG members |
|  | Circulation of the BFUG endorsed final draft of the Bucharest Ministerial Communiqué | 25 March 2012 | BFUG Secretariat |
|  | Ministerial adoption of the Bucharest Communiqué | Bucharest Ministerial Conference 26-27 April 2012 | EHEA ministers |