- Doc. Code: BFUG_DK_AZ_28_14a

- MEETING OF THE BOLOGNA FOLLOW-UP GROUP, COPENHAGEN,

- 18-19 JANUARY 2012

Information on the preparation for the Bucharest Ministerial Conference (MC) and Third Bologna Policy Forum (BPF), 26-27 April 2012

A. Progress on the draft agenda for the MC and BPF:

The draft agenda for the Bucharest MC and BPF was adopted by the BFUG in its Gödöllő meeting (17-18 March 2011). A more detailed version of the agenda is available as annex 2 of the present document, for information purposes. The two ministerial events are to take place jointly, so as to facilitate the interaction between EHEA and non-EHEA ministerial delegations, as well as international organizations. The timetable of the ministerial events starts at lunchtime on April 26 and ends with lunch on April 27. An extraordinary BFUG meeting will be organized at the same venue in the morning of April 26, to facilitate last minute discussions before the 2012 Ministerial events.

The overarching theme of the Bologna Policy Forum, as well as the sub-themes for the parallel sessions were agreed by the International Openness Working Group and communicated to the network of contact persons in order to gather their feedback. These are:

Overarching theme of the Third Bologna Policy Forum: “Beyond the Bologna process: Creating and connecting national, regional and global higher education spaces“.

Sub-themes of the four parallel sessions:

- “Global academic mobility: Incentives and barriers, balances and imbalances”;

- “Global and regional approaches to quality enhancement of HE”;

- “Public responsibility for and of HE within national and regional context”;

- “The contribution of HE reforms to enhancing graduate employability”

In order to facilitate the discussions between the Third Bologna Policy Forum participants, a brief background paper is being prepared by the International Openness WG, with the help of various organizations active on the respective topics (ACA, the E4, IAU, Council of Europe and EURASHE), which will include questions on each of the four sub-themes for the participants to engage in meaningful debates. The background paper will be submitted for BFUG discussion at the March 2012 meeting.

An ample consultation was organised by the IO WG with regard to the possible keynote speakers of the Bologna Policy Forum. A short-list of three names has been agreed between Romania, Denmark and Azerbaijan and the invitation has been sent to the first speaker on the list, Professor Elinor Ostrom, 2009 Nobel Prize winner in Economic Sciences.

B. Updates with regard to the Bucharest MC and BPF venue:

The venue for the Bucharest MC and the BPF will be the Palace of Parliament. Adequate space will be provided for bilateral meetings, upon request by various delegations.

Rooms for the accommodation of the delegations’ members will be pre-booked at hotels of different categories close to the conference venue. The full list of hotels will be provided after 15 February 2012.

C. Updates with regard to the financial aspects:

The necessary funds for organizing the EHEA 2012 Ministerial Conference and the Third Bologna Policy Forum have been approved by the Romanian Government thorough a Memorandum (21 December 2011).

D. Updates with regard to the responsibilities and consultation process:

At national level, the responsibility for organising the MC and BPF belongs to the MECTS (Ministry for Education, Research, Youth and Sports) in Romania, in cooperation with the Bologna Secretariat and UEFISCDI (Executive Agency for Higher Education and Research, Development and Innovation Funding, agency under the coordination of MECTS).

A list of countries and organisations to be invited to the Third BPF (Annex 1) has been drafted by the host country together with the BFUG Chairs at the time of the ministerial meetings (Denmark and Azerbaijan) and has been endorsed by the BFUG Board at its Copenhagen meeting (30 November 2011), following the feedback taken in after the Krakow BFUG meeting (13-14 October 2011).

The invitations for both the Ministerial Conference and the Bologna Policy Forum will be sent out in the second half of January 2012.

http://ro.wikipedia.org/wiki/Palatul_Parlamentului