Revision of ESG – time line

# Revision of ESG

Structure/Responsibilities:

E4 as mandatees

-set up

-drafting group (1 person per E plus secretary)

-steering group (2 person per E plus 1 representative of EI, BusinessEurope, EQAR-register committee, 2 persons from BFUG, plus secretary)

-decide upon final report to be presented to the BFUG

Drafting group prepares analytical paper as basis for project, consults the steering group and experts in focus groups and drafts revision report

Steering group discusses and provides feedback on drafts presented to it by the drafting group.

Methodology and structure of the project assures prime responsibility of the mandated E4 as well as broad stakeholder involvement.

Methodology:

E4 agree on purpose and scope of revision based on the ministerial mandate.  By communicating this framework E4 requests concrete suggestions for revision the ESG from stakeholders and collects respective suggestions from their constituencies while taking into consideration also the information collected in the context of the MAP-ESG project.

Based on concrete suggestions for revising the ESG a drafting group prepares drafts. The drafting group consults regularly the steering group as well as experts in order to receive feedback on own deliberations about critical and/or controversial issues.

Methodology and structure of the project assures prime responsibility of the mandated E4 as well as broad stakeholder involvement.

Time line

| 2012 |  |
| --- | --- |
| April | Ministerial Meeting in Bucharest: Mandate to E4 to revise the ESG |
| May | E4 meeting: Agreement about methodology and time line (taking into account the details of the mandate), Nomination of drafting group, Invitation to EI BusinessEurope, EQAR, BFUG to participate in steering group, Send out of request for concrete suggestions to change ESG |
| June-July | E4 and stakeholders submit concrete suggestions for revising ESG to drafting group |
| Sep-Nov | Drafting group analyses suggestions and prepares a synopsis of suggestions and an analytical paper of suggestions (issues in general; most controversial and/or open questions); 2 meetings of drafting group, in addition e-mail correspondence |
| Dec | Steering group discusses analytical paper/synopsis |
| 2013 |  |
| Jan-March | 3 focus group meetings (for ESG I, II, III each) with experts from stakeholders represented also in the Steering Group and possibly other interested parties (approx. 15 experts plus drafting group). The drafting group presents and discusses the analytical paper. Purpose is to provide the drafting group with the opportunity to discuss the crucial/controversial issues with experts. |
| March-May | Drafting group prepares the 1st draft (3 meetings, plus e-mail correspondence) |
| June | Steering group discusses the 1st draft Drafting group prepares the 2nd draft (1 meeting and e-mail correspondence) |
| July | Consultation event with open invitation to relevant stakeholders. Purpose: Discussion of 2nd draft |
| Sept-Nov | Drafting group prepares the 3rd draft (2 meetings and e-mail correspondence) |
| Nov | Steering group discusses the 3rd draft |
| Dec | Drafting group prepares the final draft (1 meeting and e-mail correspondence) |
| 2014 |  |
| Jan | E4 meeting: Approval of final report |
| Feb | Report to BFUG |