- Doc. Code: BFUG_PL_AM_26_13b

- ANNEX 1 – ROADMAP FOR BFUG CONSULTATION FOR THE THIRD BOLOGNA POLICY FORUM STATEMENT

| - Drafting phase | - When? | - Who? |
| --- | --- | --- |
| - Draft 0 of the BPF Statement is circulated to the IO WG members | - 1 October 2011 | - Romania and the BFUG Secretariat |
| - Discussion of the BPF Statement | - 9 November 2011 | - IO WG report during its Bucharest meeting |
| - Integration of the IO WG members feedback | - 10 November – 11 December 2011 | - Romania and the BFUG Secretariat |
| - Circulation of Draft 1 of the BPF Statement to the BFUG members and the national contact persons for their written feedback | - 12 December 2011 | - Romania and the BFUG Secretariat |
| - Deadline for receiving written comments from BFUG members and national contact persons to Draft 1 of the BPF Statement | - 20 January 2012 | - BFUG members and national contact persons |
| - Integrating the written comments and preparing Draft 2 of the BPF Statement | - 21 – 30 January 2012 | - Romania and the BFUG Secretariat |
| - Circulating Draft 2 of the BPF Statement to the IO WG members | - 1 February 2012 | - Romania and the BFUG Secretariat |
| - Discussing Draft 2 of the BPF Statement | - 10 February 2012 | - IO WG during its Rome meeting |
| - Integrating the comments of the IO WG and preparing Draft 3 of the BPF Statement | - 11 -19 February 2012 | - Romania and the BFUG Secretariat |
| - Circulating Draft 3 of the BPF Statement to the BFUG members and the national contact persons | - 20 February 2012 | - Romania and the BFUG Secretariat |
| - Deadline for receiving written comments to the Draft 3 of the BPF Statement | - 3 March 2012 | - BFUG members and the national contact points |
| - Integrating the comments of the BFUG members and the national contact persons and preparing the Final Draft of the BPF Statement | - 4-10 March 2012 | - Romania and the BFUG Secretariat |
| - Circulating the Final Draft of the BPF Statement to the BFUG members for endorsement and the national contact points | - 13 March 2012 | - Romania and the BFUG Secretariat |
| - Endorsing the Final Draft of the BPF Statement by the BFUG | - 19-20 March 2012 | - BFUG |
| - Adoption of the BPF Statement | - 27 April 2012 | - BPF participants |