- Doc. Code: BFUG_CY_BA_33_6.1

- Last modified: 29_08_12

# BFUG Work Plan 2012-2015

## Proposal for a BFUG decision, based on the input received by 29/08/2012

## Introduction

The 2012-2015 BFUG work plan is aimed at reflecting the main follow-up activities in line with the priorities set by the European Higher Education Area (EHEA) Ministers via the Bucharest Ministerial Communiqué. The present document was discussed for the first time in the BFUG Board meeting on 31 May 2012 in Sarajevo and it should be discussed and adopted by the Bologna Follow-Up Group (BFUG) in its meeting on 28-29 August 2012 in Cyprus.

The structure of the BFUG work plan is based on the three main political goals outlined by the Bucharest Communiqué (quality higher education for all, enhancing graduates’ employability and strengthening mobility as means for better learning) and the main priorities for action at the European level included in the final section of the Bucharest Communiqué. Based on the need to focus on full and proper implementation of the Bologna Process action lines, the future work plan makes an attempt to streamline the activity of the BFUG, as well as that of its sub-structures, in order to increase the overall transparency and effectiveness of the BFUG.

The basis for the proposal lies within the need to respond to three main questions, namely:

- What are the major challenges according to the EHEA status-quo and the Bucharest ministerial commitments?

- How to organise the follow-up work efficiently and oriented to meeting the Bucharest commitments?

- How should the EHEA interact with other areas of the world and what are the main topics of interest for future policy dialogues?

The BFUG Board recommended that the discussion on the upcoming structures underpinning the 2012-2015 BFUG work plan should start with exploring possible answers to the three questions above, which could influence the set-up of the future BFUG work. At the same time, it underlined that in order to benefit fully from having a three year work period between the ministerial conferences as well as of having the first BFUG in this period very soon after the ministerial conference in Bucharest, it is important that the BFUG not only consider, but also reach a decision on, the new work programme at its meeting in Cyprus.

Considerations regarding the proposed structure of the 2012-2015 BFUG work plan

Taking into account the focus given by the EHEA ministers through the Bucharest Communiqué, the 2012-2015 work plan has to respond to both a need for continuity and to a clear mandate for deepening and renewing the efforts for the proper and full implementation of the Bologna Process.

The BFUG Board, in its Sarajevo meeting on 31 May 2012, discussed the priorities set by the Bucharest Communiqué and considered the best structures needed in order to achieve them. Within the discussion, there was a clear agreement that a more streamlined structure is needed, which would allow the BFUG to play its role for strategic policy guidance, while concentrating on key policy issues. To ensure this, the number of working groups should be significantly reduced compared to previous years, while giving more responsibility and authority to the ones which will be operating. A structure with the BFUG as the final refiner of policy recommendations is thus envisaged and it is also recommended that each Working Group have some members who are also BFUG members. At least one of the Co-Chairs should be a BFUG member (see also below on Co-Chairs).

The proposal as it stands will require particular expertise from the Chairs of the different working groups, ad-hoc working groups and networks. Certain BFUG representatives have already informally indicated their willingness to take on particular responsibilities based on their past experience and expertise in the fields. In other cases, the role played by particular institutions in the development or use of particular tools (QF, ECTS, DS, etc.) means that they should be represented in chairing certain activities.  Between them, members of working groups should provide expertise in the main areas covered by the group and should also be reasonably representative in terms of geographical origin. Working groups should be of a workable size.

Nevertheless, given the new, broader structures and with a view to ensuring both the involvement of a wide number of countries, the BFUG Board considers necessary that as many groups as possible should be co-chaired and invites countries which have not yet done so to indicate their willingness to co-chair the various groups and sub-groups.

The proposed structure of the work plan is presented below, with a brief proposal for the mandate of various elements.

Proposal for the structure underpinning the 2012-2015 BFUG work plan

The BFUG Board proposed in its Sarajevo meeting (31 May 2012) that four main working groups are set up, bringing together the main priorities for action under each of the Bucharest Communiqué political goals:

- WG on Reporting on the Bologna Process implementation;

- WG on qualifications frameworks, recognition, quality assurance and transparency (‘Structural’ WG);

- WG on the social dimension and lifelong learning;

- WG on mobility and the external dimension of the EHEA/ internationalisation.

Each of the above mentioned working groups would have the authority to set-up ad-hoc working groups and networks, as well as to organise Bologna seminars from which policy recommendations would be collected, analysed and synthesised for BFUG discussions. The aim is to achieve more coherence and comprehensiveness in formulating policies and implementation recommendations for the BFUG to discuss and endorse prior to the 2015 Ministerial Conference in Armenia.

It is expected that the responsibilities associated with chairing the BFUG WGs would increase substantially and thus a co-chairing system would be advisable, as outlined in the section above. In this context, the BFUG Board also recommended that at least one of the WG Co-Chairs is invited to the BFUG Board meetings.  The Information on the BFUG  Proceedings would  be thus amended to this effect. A full overview of the possible areas of work and sub-structures, which could be set-up under each of the four main WGs, is available in the table below.

In terms of advancing the EHEA consolidation, the  Board will  make recommendations regarding the main tasks  for  the period of 2012-2015  for a voluntary peer learning system in the Bologna Process  which will be discussed  and endorsed by the  BFUG.   It is important that voluntary peer learning  and reviewing  system is developed  in close cooperation with the WG on Reporting on the Bologna Process implementation (in light of the overarching view on the EHEA status-quo) and the other BFUG Working Groups.In terms of the sustainability of this initiative, support could be envisaged from the upcoming EU ‘Erasmus for All’ budget and national sources, but before that, other possible sources could be identified in the existing EU financial framework and national sources, such as the programmes associated with the Eastern Partnership etc.

The main types of BFUG sub-structures used in this work plan are:

Each of the four working groups in addition to the specific tasks defined  by their respective  Terms of Referenece,  will aim through the policy recommendations developed at the end of their mandate to enhance employability, promoting lifelong learning, transversal, innovative  and entrepreneurial  skills of the graduates.

Working groups:

- a generic term used for all groups established by the BFUG in order to fulfil a complex task within the 2012-2015 work plan. The specific nature and the precise tasks of each group are outlined in the respective Terms of Reference;

- open to participation from all Bologna countries, the European Commission and the consultative members;

- their composition should reflect the diversity of the EHEA. Where necessary, the groups can also decide to set-up ad hoc working groups and networks, which can involve external experts;

- the working groups are the main BFUG structures which can make policy recommendations, based on their Terms of Reference and the results of the ad-hoc working groups and networks under their direct coordination;

- it is advisable that each working group is coordinated by two co-chairs, at least one of which should be a BFUG member. One representative of the Co-Chairing team should attend the BFUG Board meetings, in order to ensure the coherence of the communication and of the documents discussed by the BFUG;

- the WG should report back to the BFUG. The final reports / conclusions and policy recommendations for the 2012-2015 period should be presented and discussed no later than the BFUG meeting in the fall of 2014 and only in case of the WG on the  Reporting of the Bologna Process Implementation  the deadline should be extended to January, 2015.

Ad-hoc working groups:

- not a permanent structure, but smaller working groups to be established by the BFUG working groups or by the BFUG/ BFUG Board in order to fulfil a specific task within a limited timeframe dependent on the task at hand (shorter than the  three-year period);

- can develop policy recommendations to be submitted to their coordinating structure (either the BFUG or a Working Group);

- their composition should reflect the task at hand and be chaired by a BFUG member.

Networks:

- they should be established by the BFUG working groups or by the BFUG/ BFUG Board;

- are meant to establish longer term cooperation between a large number of partners (potentially all countries and organisations participating in the Bologna Process);

- in terms of activity, these networks connect experts in a specific field (e.g. student support, recognition of prior learning or qualifications frameworks) from different countries and organisations and allow them to share information and examples of good practice, to assist each other, and possibly also to develop new policies, if this is clearly outlined in the Terms of Reference;

- are not expected to issue policy recommendations unless otherwise stated in the Terms of Reference;

- should be connected to a specific working group and include at least a BFUG member (preferably also one of the Co-Chairs of the ‘parent’ WG) in the meetings if only composed of national experts, in order to allow for good communication with the BFUG as a whole.

Seminars/Conferences:

- The EHEA has an open calendar of events, situated on the home page of the EHEA permanent website (www.ehea.info);

- The EHEA members and consultative members are encouraged to arrange seminars, conferences and workshops along the priorities set by the Bucharest Communiqué.

- For an event to be included in the calendar of events that is published on the official EHEA website, it obviously has to be related to the Bologna Process and should be organised or at least supported by one of the countries/ organisations participating in the Bologna Process or by a BFUG WG. Moreover, it should in principle be open to participants from all Bologna countries, which however does not exclude international events that have a more regional focus.

- Invitations, presentations, reports and conclusions can be published on the website and forwarded to the BFUG upon request of the organisers.

A more comprehensive list of working methods which could be employed in implementing the BFUG 2012-2015 work plan is to be found within the ‘Background paper on additional working methods to facilitate the proper and full implementation of the agreed Bologna principles and action lines’:

http://bfug.ehea.info/bfug3/Documents/BFUG/2011,%2017-18%20March,%20Gödöllő/BFUG_HU_AD_24_10a%20Additional%20working%20methods.pdf

This list of possible follow-up activities at European level does not claim to be comprehensive and the BFUG is actively encouraged to develop additional forms of cooperation taking forward the different priority areas at European level that can feed into the political decision-making process.

The draft Terms of References for BFUG WGs are enclosed as annexes to the present draft document, which will be discussed and endorsed at the Nicosia BFUG meeting on 28-29 August.

BFUG proposed structures underpinning the 2012-2015 work plan

| Proposed WG | Proposed Co-Chairs | Corresponding priority for action within the Bucharest Communiqué | Main tasks | Proposed participants |  |
| --- | --- | --- | --- | --- | --- |
| WG on Reporting on the Bologna Process Implementation | Andrejs Rauhvargers (Latvia) Germain Dondelinger (Luxembourg) | Ask Eurostat, Eurydice and Eurostudent to monitor progress in the implementation of the Bologna Process reforms and the strategy “Mobility for better learning”; We ask for more targeted data collection and referencing against common indicators, particularly on employability, the social dimension, lifelong learning, internationalisation, portability of grants/loans, and student and staff mobility. | Assess the progress made with the implementation of Bologna reforms and the implementation of the strategy ‘Mobility for better learning’ In cooperation with the WGs to develop a structured and standardised monitoring system consisting of indicators and qualitative analysis to evaluate the progress towards 2015 in core policy areas, like social dimension, mobility, implementation of structural reforms, etc. Produce one joint, comprehensive report, based on clear indicators, set for countries and qualitative analysis, on the implementation of the Bologna Process from a governmental perspective, to be complemented by other reports from the consultative members To support the development of a voluntary peer learning system and reviewing in the Bologna Process [For draft ToR, see Annex1] | Austria Belgium/Flemish Community Finland France Germany Arūnas Mark (Lithuania) Norway Romania Turkey EC EI ENQA ESU EURASHE Euridyce EUROSTAT EUROSTUDENT |  |
| Proposed WG | Proposed Co-Chairs | Corresponding priority for action within the Bucharest Communiqué | Main tasks | Proposed participants |  |
| WG on qualifications frameworks, recognition, quality assurance and transparency (‘Structural’ WG) | Noel Vercruysse (Belgium/Flemish Community) Friedrich Bechina (Holy See) Bartlomiej Banaszak (Poland) Sjur Bergan (CoE) | Coordinate the work of ensuring that qualifications frameworks work in practice, emphasising their link to learning outcomes and explore how the QF-EHEA could take account of short cycle qualifications in national contexts. Design and support initiatives building on the recommendations of the Recognition Working Group. Support the implementation of the Lisbon Recognition Convention, overseen by the Lisbon Recognition Convention Committee, as applied to the EHEA, including by assisting member countries to ensure conformity of their legislation with LRC commitments, jointly with the ENICs/NARICs and other stakeholders. Further efforts to facilitate and improve cross border recognition of qualifications, including through the wide use of the European Area of Recognition manual and taking account of the long term objective of the automatic recognition of comparable academic degrees. Facilitate the coherence between national and EU legislation on professional qualifications with the EHEA (e.g. reference to learning outcomes, promoting even greater comparability in the use of ECTS as the basis for such recognition). Develop EHEA guidelines for transparency policies and continue to monitor current and developing transparency tools. Work to ensure that the ECTS Users’ Guide fully reflects the state of on-going work on learning outcomes and recognition of prior learning. Promote quality, transparency, employability and mobility in the third cycle, while also building additional bridges between the EHEA and the ERA. Allow EQAR-registered quality assurance agencies to perform their activities across the EHEA, while complying with national requirements. | In co-operation with the ENIC and NARIC Networks, the Network of national QF correspondents, and ENQA, to develop policy proposals aiming to improve the interaction between qualifications frameworks, quality assurance, and the recognition of qualifications and transparency intruments; Develop policy proposals aiming to enhance and improve transparency instruments for describing individual qualifications as well as higher education systems, in particular as concerns the Diploma Supplement and the ECTS. In this, the Working Group should establish cooperation with the institutions and bodies charged with the oversight and implementation of the relevant transparency instruments; Comment, as appropriate, on draft ammendments to the European Standards and Guidelines; Engage in a dialogue with the European Commission and the national authorities responsible for professional qualifications in order to establish effective cooperation to facilitate the coherence between the national and EU legislation on professional qualifications within the EHEA. Provide input to the working group(s) responsible for international openness and the social dimension on the role of structural reforms in furthering the goals of these groups; Contribute to the general aim of enhancing employability of graduates within the EHEA through the full an proper implementation of Bologna tools; Organise, or stimulate the organisation of, Bologna conferences, mini-seminars and events on issues related to structural reform; Comment on findings on pathfinding group on automatic recognition. Submit policy proposals to the 2015 Ministerial conference, through the BFUG, aiming to improve the coherence of the structural reforms of the EHEA; Cooperate with EQAR on better recognition of its role towards the national governments. Coordinate the work of ensuring that qualifications frameworks work in practice, emphasising their link to learning outcomes and explore how the QF- EHEA could take account of short cycle qulifications in national contexts; [For draft ToR, see Annex2] | Armenia Austria Belgium/French Community Croatia Věra Šťastná (Czech Republic) Ditte Mesick (Denmark) Finland Germany Ireland Artūras Grebliauskas/Aurelija Valeikienė (Lithuania) Maria de Lurdes Correia Fernandes (Portugal) Romania Sweden Switzerland the Netherlands Turkey EC EI ENQA EQAR ESU EUA EURASHE |  |
| Proposed Sub-structure of the WG | Proposed Co-Chairs | Corresponding priority for action within the Bucharest Communiqué | Main tasks | Proposed participants |  |
| Network of National Correspondents | Council of Europe | Coordinate the work of ensuring that qualification frameworks work in practice, emphasising their link to learning outcomes and explore how the QF-EHEA could take account of short cycle qualifications in national contexts | Facilitate the sharing of experience in the development of national qualifications frameworks compatible with the overarching framework of qualifications of the EHEA (QF-EHEA) as well as with the EQF. Provide a forum for national correspondents to exchange experience and to discuss issues of particular relevance to the development and implementation of national frameworks. [ToR to be finalised] | One representative of each EHEA member state, the European Commission, consultative members, CEDEFOP, ETF |  |
| Proposed ad-hoc WG on the revision of the ECTS Users’ Guide | (TBC) | Work to ensure that the ECTS Users’ Guide fully reflects the state of on-going work on learning outcomes and recognition of prior learning | Aid HEIs in their work to further link study credits with both learning outcomes and student workload, and to include the attainment of learning outcomes in assessment procedures. Work to ensure that the ECTS Users’ Guide fully reflects the state of on-going work on learning outcomes and recognition of prior learning [ToR to be defined] | Armenia Austria Belgium/Flemish Community Italy Raimonda Markevičienė (Lithuania) EC |  |
| Proposed ad-hoc WG on the second and third cycles | Aarhus University (Denmark) Nicola Vitorio/ Marzia Foroni (Italy) Romania Spain EUA | Promote quality, transparency, employability and mobility in the third cycle, while also building additional bridges between the EHEA and the ERA | Map the current arrangements for the second and third cycle in the EHEA, taking into account also the developments within the ERA Explore the need and feasibility of developing common principles for the third and second cycle programmes within the EHEA [For draft ToR, see Annex5] | Armenia Austria Belgium/Flemish Community Belgium/French Community Czech Republic France Ireland Poland EC |  |
| Proposed WG | Proposed Co-Chairs | Corresponding priority for action within the Bucharest Communiqué | Main tasks |  | Proposed participants |
| WG on the social dimension and lifelong learning | Brian Power (Ireland) Karina Ufert (ESU) | Widening access to higher education is a precondition for societal progress and economic development. We agree to adopt national measures for widening overall access to quality higher education. We will work to raise completion rates and ensure timely progression in higher education in all EHEA countries. The student body entering and graduating from higher education institutions should reflect the diversity of Europe’s populations. We will step up our efforts towards underrepresented groups to develop the social dimension of higher education, reduce inequalities and provide adequate student support 2 Lifelong learning is one of the important factors in meeting the needs of a changing labour market, and higher education institutions play a central role in transferring knowledge and strengthening regional development, including by the continuous development of competences and reinforcement of knowledge alliances. Develop a system of voluntary peer learning and reviewing by 2013 in countries which request it and initiate a pilot project to promote peer learning on the social dimension of higher education. Establish conditions that foster student-centred learning, innovative teaching methods and a supportive and inspiring working and learning environment, while continuing to involve students and staff in governance structures at alllevels. | Step up the efforts towards strengthening policies of widening access and raising completion rates, including measures targeting the increased participation of underrepresented groups. Support the development of national access policies by elaborating core indicators that may be used for measuring and monitoring the relevant aspects of the social dimension in higher education, including lifelong learning. To identify obstacles to participation and analyse best practice examples of how some countries have overcome these obstacles. To promote the development of national/regional strategies at governmental level to widening access to Higher Education and mainstream lifelong learning approaches in higher education. Support the development of a pilot project to promote peer learning on social dimension with a general oversight mandate to further BFUG social dimension goals. Consider and make recommendations on specific policy issues related to the social dimension of higher education and lifelong learning, taking into account the insights of the Implementation Report. Address the new pedagogical and didactical requirements which follow from a more diversified student population, the WG shall analyse and share good practices and give recommendations on how to develop the student-centred learning in correlation with other needed reforms. To reach this goal, a more supportive and inspiring working and learning environment for staff and students is needed as well as better engagement of students and staff in governance structures. [For draft ToR, see Annex3] |  | Armenia Austria Belgium/Flemish Community Finland Germany Inese Sture (Latvia) Inga Milišiūnaitė (Lithuania) Norway Romania EC EI |
| Proposed Sub-structure of the WG | Proposed Chair (s) | Corresponding priority for action within the Bucharest Communiqué | Main tasks | Proposed participants |  |
| Recognition of Prior Learning (RPL) Network | Estonia | N/A | Help promote and inform the effective use and practice of RPL across participating countries Provide a means for member countries to share and learn from policies and practice across Europe in relation to RPL development Build links between European countries at various stages in RPL development [ToR to be further developed] | Armenia Austria Belgium/Flemish Community Ireland Poland Romania Switzerland the Netherlands |  |
| Proposed WG | Proposed Co-Chairs | Corresponding priority for action within the Bucharest Communiqué | Main tasks | Proposed participants |  |
| WG on mobility and internationalisation | Gottfried Bacher (Austria) Peter Greisler (Germany) Romania | Evaluate the implementation of the “EHEA in a Global Setting” Strategy Promote mobility as an integral part of the efforts to further internationalising Higher Education in the EHEA. | Contribute to the implementation of the 2012 EHEA ‘Mobility for Better Learning’ Strategy and to the evaluation of the 2007 ‘EHEA in a Global Setting Strategy’. Support efforts to build mobility and internationalisation strategies at the national level. Develop a policy proposal for a specific European accreditation approach for Joint programmes, which should be applied to all those Joint programmes that are subject to compulsory programme accreditation at national level. Propose recommendations on improving staff mobility. Explore options of improving the information on study programmes and admission systems in the EHEA (measure 8 of the mobility strategy) Explore whether a common approach on the portability of grants, loans and scholarships is feasible and to be recommended Examine options of assessing and improving the international attractiveness of the EHEA and to propose a target on mobility into the EHEA Propose guidelines for further internationalisation developments in the EHEA. Consider and make recommendations on specific policy issues related to mobility and internationalisation of the EHEA. [For draft ToR, see Annex4] [Possible sub-structures to be defined] | Armenia Belgium/Flemish Community Belgium/French Community Denmark Jolita Butkienė (Lithuania) Poland Spain the Netherlands Turkey Council of Europe EI EC ENQA ESU |  |
| Proposed sub-structure of the WG | Proposed Co-Chairs | Corresponding priority for action within the Bucharest Communiqué | Main tasks | Proposed participants |  |
| Network of Experts on Student Support in Europe (NESSIE) | Germany Norway Romania | N/A | Exchange information and to provide assistance in facilitating the portability of grants and loans Work on the promotion of positive incentives for the portability of grants and loans Explore the feasibility of a pan-European financial scheme to support mobility | The mandate of the current participants will be confirmed when requested. Austria (confirmed) Belgium/Flemish Community (confirmed) Czech Republic (confirmed) Denmark (confirmed) Poland (confirmed) Sweden (confirmed) the Netherlands (confirmed) |  |
| Proposed structures/ activities directly responsible to the BFUG | Proposed Co-Chairs | Corresponding priority for action within the Bucharest Communiqué | Main tasks | Propsed participants |  |
| BFUG ad-hoc WG on Higher Education Financing and Governance | Armenia Denmark Romania | Bucharest Communiqué excerpt: ‘…and acknowledge the need to open a dialogue on funding and governance of higher education. We recognise the importance of further developing appropriate funding instruments to pursue our common goals.’ | Present proposals for how to support the modernisation of governance and financing [For draft ToR, see Annex6] | Austria Belgium/Flemish Community Czech Republic Norway |  |
| Definition of the voluntary peer learning and reviewing in the Bologna Process (conducted by the BFUG Board in close cooperation with the WG on Reporting on the Bologna Process and other BFUG WGs) | BFUG Chairs / BFUG Board Denmark Romania | Develop a system of voluntary peer learning and reviewing by 2013 in countries which request it and initiate a pilot project to promote peer learning on the social dimension of higher education | Develop a system of voluntary peer learning and reviewing and define themes relevant to the Bucharest Communiqué priorities based on proposals from the BFUG WGs. [ToR (and further implementation) to be defined] | BFUG Board members |  |

European Commission (2009): "ECTS Users’ Guide", http://ec.europa.eu/education/lifelong-learning-policy/doc/ects/guide_en.pdf