- Doc. Code: BFUG_GR_KZ_39_5b

- Last modified:01.04.2014

Roadmap for the Discussion of the Future of the Bologna Process

| When | What | Who |
| --- | --- | --- |
| 12 February 2014, Astana | Launching the discussion | Several countries and stakeholders |
| 28 March 2014 | Drafting (the Bologna Process revisited) of the non-paper | Several countries and stakeholders |
| 8 April 2014, Athens | Continuation of the discussion at the Co-Chairs’ Coordination meeting | Meeting participants |
| 9-10 April 2014, Athens | Continuation of the discussion | BFUG members |
| 20 June 2014 | 2nd version of the non-paper | Several countries and stakeholders |
| 9-10 July 2014, Italy | Discussion of the 2nd version of the non-paper | BFUG Board |
| 18-19 September 2014, Italy | Extraordinary BFUG meeting on the Future of the Bologna Process | BFUG members |
| 1 November 2014 | 3rd version of the non-paper | Several countries and stakeholders |
| 27-18 November 2014, Italy | Discussion of the 3rd version of the non-paper | BFUG members |
| December 2014 | Consultation of the revised version of the non-paper | BFUG Board |
| 26-27 January 2015 | Discussion of the final version of the non-paper and endorsement | BFUG |
| 14-15 May 2015 | Presentation of the document at the Yerevan Ministerial Conference |  |