Doc. Code: BFUGBoard_IT_VA_40_6a

Draft 12.Jun 2014

BFUG Working Group "Reporting on the Implementation of the Bologna Process"

Report to BFUG Board meeting in Rome, Jul 9 2014

Please note that this report is compiled 3 weeks before the WG Reporting meeting which will be held in Riga, Jul 2. 
The oral presentation at the Board meeting will include the outcomes of the WG meeting

In this period since the Board meeting in Astana, the Working group has:

- reported to the BFUG meeting on 9-10 Apr BFUG in Athens;

- held a WG meeting on 2 July, 2014 in Riga;

- started analysing the data received from 32 countries

## Key Issue

At the day of compiling this document – 45 days after the deadline – at least 15 countries still have NOT submitted the finalised, completed questionnaire.  Since in a couple of cases there have been some misunderstandings due to the features of the system, the Secretariat is currently contacting those countries to clarify the situation and issuing another reminder.

The absence of 1/3 of the countries does not allow the data collectors and the working group to start the data analysis properly.  Any indications of the main trends may change (or even turn around) when the data of the last 1/3 countries come in. And if so, any chapter drafts may need re-writing rather than updating.  Also, for some scorecard and non-scorecard indicators preliminary maps have been prepared. However, due to the large amount of missing country information the maps so far are not sufficiently informative, and this work will have to be re-done as more information is submitted.

It is indeed surprising that, despite considerable discussion in the BFUG and agreement on the importance of respecting deadlines, such a large number of countries have again failed to fulfil their duties.

## Status quo

Data collectors have carried out test runs using the data available and are fully ready to continue their job. As well as integrating Eurostudent and Eurostat data when it becomes available (as planned) the data collectors will also have to work with a significant amount of, as yet unsubmitted, country data. The process for the data collectors will therefore be more intense than expected.

WG Reporting will meet on Jul 2 in Riga.

The agenda of the working group will include:

- information on the state of art of the data collection followed by WG discussion on the first results;

- discussion on indicators and

- discussion of the next steps towards preparation of the report.

## Important deadlines

| Jan 31, 2014 | Sending questionnaire to countries |
| --- | --- |
| Feb 12, 2014 | WG Reporting to BFUG board in Astana |
| Apr 9-10, 2014 | WG Reporting to BFUG board in Athens |
| Apr 30, 2014 | Deadline for data submission |
| May 1, 2014 | Analysis of material, and development of planning for integrating data from Eurostat, Eurostudent and Eurydice and consultation with the relevant working groups |
| Jul 2, 2014 | WG meeting in Riga: first discussion of the structure of the implementation report, draft chapters; scorecard indicators |
| September 18-19, 2014 | BFUG meeting - presentation of preliminary results. |
| - November 5, 2014 | WG Implementation meeting in Luxembourg : Second discussion on the draft report, finalisation of the scorecard indicators and discussion of issues for conclusions and recommendations. |
| 2015 |  |
| January 13, 2015 | WG meeting in Riga: last amendments to final report |
| January 26-27, 2015 | BFUG: discussion of draft integrated report and of the conclusions prepared by the WG Implementation |
| March 24-25, 2015 | Print-ready electronic version of the integrated report provided to BFUG |
| May 2015 | Presentation of final integrated report to the ministerial conference |