Doc. Code: BFUG_IT_VA_41_10

- Roadmap for Drafting the Yerevan Ministerial Communiqué

The current paper presents the roadmap for drafting the Yerevan Ministerial Communiqué taking into consideration the recommendations of the Board made at its meeting on 9 July 2014 in Vatican City. As for the drafting of the Communiqué the Board recommended establishing a drafting group composing of the representatives from Italy and Holy See as present Co-Chairs as well as Latvia and Iceland as the upcoming Co-Chairs and Armenia as a Vice Chair and the Secretariat.

| No. | Yerevan Communiqué | When? | Who? |
| --- | --- | --- | --- |
|  | Making recommendations on the main concept and format of the Yerevan Communiqué | Holy See BFUG Board meeting 9 July 2014 | BFUG Board |
|  | Adoption of the roadmap | Rome BFUG meeting 18-19 September 2014 | BFUG |
|  | Consideration of the conclusions of the dialogue on the Future of the Bologna Process and of the reports from the BFUG WGs (excluding the implementation WG). | Rome BFUG meeting 27 – 28 November | BFUG |
|  | Circulating draft 0 of the Yerevan Communiqué | 12 January 2015 | BFUG Secretariat (deadline for the BFUG documents) |
|  | Discussing draft 0 of the Yerevan Communiqué | Riga BFUG meeting 26-27 January 2015 | BFUG |
|  | Redrafting the documents according to the comments of the BFUG | 28 January 2015 – 4 February 2015 | Drafting group and the Secretariat |
|  | Circulating of draft 1 of the Yerevan Communiqué | 9 February 2015 | BFUG Secretariat (deadline for the BFUG Board documents) |
|  | Discussing draft 1 of the Yerevan Communiqué | Reykjavik BFUG Board meeting 24 February 2015 | BFUG Board |
|  | Integrating feedback received during the Reykjavik BFUG Board meeting | End of February 2015 | Drafting group and the Secretariat |
|  | Circulation of draft 2 of the Yerevan Communiqué to the BFUG for written comments | 9 March 2015 | BFUG Secretariat |
|  | Receiving final comments from BFUG members | 16 March 2015 | BFUG Secretariat |
|  | Integrating the feedback received from BFUG members | 16-19 March 2015 | Drafting group and the Secretariat |
|  | Circulating draft 3 of the Yerevan Communiqué to the BFUG members | 20 March 2015 | BFUG Secretariat |
|  | Discussing draft 3 of the Yerevan Communiqué and the adoption by the BFUG of the FINAL VERSION to be submitted to EHEA Ministers for adoption on May 14-15 | Riga BFUG meeting 24-25 March 2015 | BFUG |
|  | Circulation of the BFUG endorsed draft of the Yerevan Ministerial Communiqué | 29 March 2015 | BFUG Secretariat |
|  | Ministerial adoption of the Yerevan Communiqué | Yerevan Ministerial Conference 14-15 May 2015 | EHEA ministers |

The conclusions of the dialogue on the Future of the Bologna Process and of the WG reports are connected with the Communiquè as background materials.