Roadmap (to be filled in at the meeting)

| Timing | Event | I) Roles of authorities, HEIs, ENIC/NARICs in implementing recommendations | II) considerations for reviewing legislation | III) differences in recognition criteria and procedures/ more equal treatment in EHEA | IV) quality of the recognition procedures in the internal quality procedures | V) role of QFs in implementing the recommendations (with WG QF) | Improving recognition with other parts of the world |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 15/02/ 2010 | WG meeting in Brussels, | Discussion of Terms of Reference of the Working group, setting road map and timetable |  |  |  |  |  |
| Mar-May/ 2010 |  | Gathering ideas from WG members, consultations with stakeholders | Listing first ideas on recommendations | ENIC/NARICs and HEIs (questionnaire?) | Consultations with bodies involved in QA and representatives of HEIs | Consultations with WG QF | Gathering ideas from WG members, Contacts with WG global dimension |
| 27 or 28 /05/2010 | WG meeting (Location?) | Brainstorming on possible recommendations | Discussion of document presented | Brainstorming on possible recommendations | Brainstorming on possible recommendations | Brainstorming on possible recommendations | Brainstorming on possible recommendations |
| 21-22/ 06/2010 | ENIC-NARIC meeting | Discussion of all issues with ENIC and NARIC networks, gathering opinions and information |  |  |  |  |  |
| Jul-Oct/2010 | Preparing first draft of recommendations |  |  |  |  |  |  |
| Autumn 2010 | BFUG meeting | Intermediate reporting to BFUG |  |  |  |  |  |
| Oct-Nov/2010 | WG meeting (Location?) | Discussing and revising first draft of recommendations |  |  |  |  |  |
| Nov 2010-Jan 2011 | Preparing documents and organising for a stakeholder meeting |  |  |  |  |  |  |
| Feb/Mar 2011 | Stakeholder meeting – conference? Seminar? (Location? sponsors? Perhaps attached to BFUG?) | Discussing issues and draft recommendations with policy makers, recognition specialists, HEIs, QA agencies etc. |  |  |  |  |  |
| Spring 2011 | BFUG meeting | Intermediate reporting to BFFUG |  |  |  |  |  |
| Apr-May 2011 | Finalising drafts |  |  |  |  |  |  |
| Jun 2011 | WG meeting (attached to ENIC/NARIC?) | Approval of recommendations by WG |  |  |  |  |  |
| Autumn 2011 | BFUG meeting | Submission of recommendations to BFUG |  |  |  |  |  |