|  | Date: 19 May 2011 6th meeting of the IO WG Agenda point: 4 |
| --- | --- |

- CONCEPT PAPER

regarding the organisational process of the 3rd Bologna Policy Forum in Bucharest, Romania

- Purpose of the concept paper

Following the:

- feedback provided by the members of the International Openness Working Group (IO WG) in the last meetings held in Bucharest on 28 October 2010 and Vienna on 18 January 2011,

- input given the Bologna Follow-Up Group (BFUG) members during the meeting held in Gödöllő on 17-18 March 2011,

there was a clear preference for a democratic and inclusive organisational process of the third edition of the Bologna Policy Forum (3rd BPF) to be held in Bucharest, on 26-27 April 2012, in connection with the Bologna Process Ministerial Conference.

Such a democratic process needs a transparent timeline and clear outcomes and as such, a roadmap outlining the steps to be taken in the preparation of the 3rd BPF was needed, in order to allow for enough consultation and inclusion of all interested parties.

- Aim and structure of the concept paper

The present paper will aim at:

- Presenting the proposed involvement of different actors who will be active in organisational matters, both on content preparations and logistics;

- Presenting the draft timeline of the BPF preparations, as well as the main milestones to be taken into consideration by the members of the IO WG (Annex 2);

- Introducing the previous choices with regard to the selection mechanisms of the countries and organisations to be invited and collecting the IO WG members input with regard to how this matter could be handled for the 3rd BPF;

- Introducing the previous language regime used and the proposed language regime for the Bucharest Ministerial Conference and the 3rd Bologna Policy Forum;

- Introducing the overarching theme, the proposed sub-themes and the agenda for the Ministerial Conference and the Third Edition of the BPF to be held in Bucharest on 26-27 April 2012 (Annex 1);

- Introducing possible suggestions for organising the parallel sessions and collecting the IO WG members input on background papers and keynote speakers;

- Introducing the main aims and structure of the 3rd BPF statement.

- Actors involved in the 3rd BPF preparations

- The Ministry of Education, Research, Youth and Sports in Romania (Ministerul Educatiei, Cercetarii, Tineretului si Sportului - MECTS)

The MECTS in Romania will organise the Third Edition of the BPF, as an official host of the event and in its capacity as Vice-Chair of the BFUG between 1 July 2010 and 30 June 2012. In the process of organising the 3rd BPF, the MECTS will closely consult with the BFUG Chairs and will benefit from the inputs given by the International Openness WG. The MECTS will cooperate with the Bologna Follow-Up Group Secretariat in the process of organising the BPF and will seek the endorsement of the 3rd BPF agenda and organisational handbook from the BFUG.

- The Bologna Follow-Up Group (BFUG)

The BFUG will oversee the preparation process for both the 2012 Bucharest Ministerial Conference and the 3rd Bologna Policy Forum. In addition, the BFUG provided feedback to the 3rd BPF agenda and endorsed its final version at the last meeting in Gödöllő and will do as such for the 3rd BPF organisational handbook. The BFUG has delegated the support for the preparations of the 3rd BPF to the International Openness Working Group (IO WG), through its Terms of reference adopted in May 2010.

- The BFUG Chairs

According to the current arrangements, endorsed by all the EHEA members during the 2010 Budapest and Vienna Ministerial Conference, the BFUG Chairs have a joint responsibility to take forward the aims and actions laid down by Ministers responsible for Higher Education in the Bologna Declaration and subsequent Communiqués of Ministerial Conferences. As such, they chair both the Bologna Ministerial Meetings and the Bologna Policy Forum and they cooperate with the MECTS of Romania in the preparations for the Bucharest events, especially in connection with the protocol required and the political direction of the event.

- The International Openness Working Group (IO WG)

The IO WG Terms of reference clarify that the group is to “support the host country Romania in preparing the Third Bologna Policy Forum with regard to both the organisational aspects and the content – involving non-EHEA countries that nominated a national contact person for the follow-up to the Second Bologna Policy Forum by way of electronic consultation”. Concretely, the IO WG is active in all stages of the 3rd BPF preparations, by providing feedback to the MECTS of Romania regarding the various aspects of the BPF: organisational timeline, programme, participation, protocol etc.

- The National Contact Persons (NCP)

As the aim of the BPF is to enhance the policy dialogue between countries interested in the developments of the EHEA and the EHEA members, all the countries and organisations participating in the 2nd BPF were invited to nominate one contact person each for the follow-up. Additionally, the countries which had reacted positively to the invitation but in the end could not attend were also asked to nominate one contact person each.

So far, the Bologna Secretariat has received 17 nominations from non-EHEA countries and 31 from EHEA countries (the BFUG members are currently considered as contact persons in the cases in which no concrete name was given). The total number of contact persons is now 51 from 48 countries and organisations.

The network of national contact persons will be providing feedback to the preparations of the 3rd BPF by way of electronic consultation, including an interactive online forum (http://forum-bologna.uefiscsu.ro/). The aim is to ensure a high level of ownership of the 3rd BPF theme and programme structure also from the side of non-EHEA countries, while ensuring the success of the policy dialogue through increased interaction and relevance of the agenda.

- Bologna Follow-Up Group Secretariat

According to its Terms of Reference adopted by the BFUG, one of the agreed functions of the Bologna Follow-Up Group Secretariat is to cooperate with the MECTS in Romania in organising the Ministerial Conference in Bucharest and the 3rd BPF. The BFUG Secretariat will be involved in the organisational process of the 3rd BPF and will support the MECTS in Romania, as well as all other parties involved in the 3rd BPF preparations.

Additionally, the BFUG Secretariat will be responsible with communicating to the contact persons nominated by the second BPF participants and consulting them on the organisational process, as well as on the possible sub-themes to be discussed in the parallel sessions of the BPF. The consultation process is ongoing and some feedback on the preferred sub-themes has already been received.

- Draft timeline of the 2012 Bucharest BPF preparations

An updated timeline for the 3rd BPF preparations is included in Annex 2 of the present document. This timeline is being updated according to the dates of the various BFUG and Board meetings, as well as to the endorsed Work Plan of the IO WG.

- Possible selection mechanisms of the countries and organisations to be invited to the Third BPF

Since the BPF is a policy dialogue event that is logistically restricted in its size, a decision regarding the non-EHEA countries to be invited had to be taken before each edition.

For the First BPF, the decision on the 20 countries to be invited had been taken by the Benelux hosts and the Czech Presidency. These countries were: Australia, Brazil, Canada, P.R. China, Egypt, India, Israel, Japan, Jordan, Kazakhstan, Kyrgyzstan, Mexico, Morocco, New Zealand, Senegal, South Africa, Tanzania, Tunisia, USA, Vietnam. After the invitations had been issued, three more countries expressed their interest to attend the BPF and were thus informally invited: Chile, Ethiopia, Thailand. [The 15 countries in italics are the ones that in the end were represented during the First BPF]

For the Second BPF, the decision on the 34 countries that were invited had been taken by the Hungarian and Austrian hosts and the Spanish EU Presidency, with the consultation of the International Openness Working Group and UNESCO. These countries were: Argentina, Australia, Brazil, Canada, Chile, China (P.R.), Colombia, Costa Rica, Egypt, Ethiopia, Ghana, India, Indonesia, Israel, Japan, Jordan, Korea (South), Kyrgyzstan, Lebanon, Malaysia, Mali, Mexico, Morocco, New Zealand, Peru, Philippines, Saudi Arabia, Senegal, South Africa, Tanzania, Thailand, Tunisia, the United States of America and Vietnam. Additionally, the OECD and the International Association of Universities (IAU) were also invited and attended the event. [The 24 countries in italics are the ones that in the end were represented during the Second BPF]

For the Third BPF, the most probable location is the Palace of Parliament in Bucharest in which the plenary room can logistically fit around 100 heads of delegation plus the presidium. In this situation, the proposal is that the host country continues to address invitations to the countries which were already invited to the first two editions of the BPF and to add additional countries based on consultations with UNESCO, the IO WG and the BFUG. In this sense, UNESCO has kindly agreed to provide 10 countries with interest in the EHEA developments from each UNESCO region (which would include the ones which were already previously invited in the 1st and 2nd BPFs), in consultation with its regional offices.

The final decision on the list for countries to be invited would lie with the host country - Romania and the BFUG Chairs for the first semester of 2012 – Denmark and Azerbaijan, in consultation with the IO WG and the BFUG, similarly to the system used in previous editions of the BPF.

As the IO WG members have expressed their interest in the last IO WG meeting in Vienna (18 January 2011), international organisations from various parts of the world will also be invited to take part in the 3rd BPF. A call for consultations on this topic has been launched via e-mail by the BFUG Secretariat and a list of possible international organisations has already emerged following the responses from IAU, ESU and UNESCO (Annex 3). The IO WG members are invited to express their opinion on which organizations to be invited.

- Process for finalising the agenda of the 3rd BPF

As a result of the last IO WG meetings (18 January 2011, Vienna), two versions of the draft agenda for the 3rd BPF were proposed. One version was similar to the one proposed for the IO WG meeting on 28 October 2010, with small amendments including bilateral meetings in the late evening of the first day or in the morning of the second day, if possible, and a second version which was shorter – from 26th April lunchtime to 27th April lunchtime. At the BFUG meeting in Gödöllő, the short version of the agenda (lasting one day, from 26 April 2011 at lunchtime to 27 April 2011 at lunchtime) was endorsed (Annex 1). Further minimal amendments might be made by the host country depending on developments on the logistical side and will be brought to the attention of the IO WG and the BFUG.

With regard to the 3rd BPF overarching theme and sub-themes for the parallel sessions, following the discussions at the last IO WG meeting, an online call for consultations was launched and two more formulations for the overarching theme were received from IAU and EUA, in addition to the one resulted from the previous IO WG meeting. For the BFUG meeting, a short list of themes was put forward for endorsement (Annex 4).

The proposal “Beyond the Bologna process: Creating and connecting national, regional and global higher education spaces” was preferred by most BFUG members and it was endorsed as the 3rd BPF overarching theme. For the sub-themes, an agreement was reached amongst the BFUG members for:

- mobility (sub-themes 1a and 1b)

- quality assurance (sub-themes 6a and 6b)

- social (international) responsibility  (subthemes 3 and 4)

- For the fourth subtheme a choice or a combination of employability and transparency is expected to be decided on. It was also agreed that the IO WG has to refine the sub-themes and present them to the BFUG at the following meeting for final endorsement.

For the 3rd BPF parallel sessions, the proposed format would be to include background papers on the main topics to be debated and to have moderated debates based on pre-set questions. In this regard, the IO WG members are invited to come up with suggestions for possible keynote speakers for the BPF official opening and possible sources for background papers.

With regard to the 3rd BPF statement, the IO WG members are asked to define its main aims and structure, while deciding whether it should be focused on political declarations or action lines. Based on the responses received, the IO WG will take additional steps in preparing a draft version of the statement to be discussed and refined at the next WG meeting (9 November 2011, Bucharest). The main outline should be presented at the next BFUG meeting in October for endorsement.

The national contact persons were informed about the latest developments regarding the 3rd BPF via e-mail. The endorsed overarching theme and possible sub-themes were brought to their attention, while requesting feedback on these topics. A number of responses have already been received by the BFUG Secretariat.

Finally, as it was proposed to have an additional IO WG meeting before the 2012 Bologna Policy Forum in Bucharest in order to endorse the final arrangements for the BPF sessions as well as the content of the BPF statement, it should be discussed by the IO WG when this meeting should take place (preferably in January/ February 2012) as well as a possible location, within easy reach from most of the IO WG participants.

- Language regime

The provisions regarding the language regime for the 2nd BPF were the following:

“The conference language will be English, with interpretation from and into French, German, Russian and Spanish in all plenary sessions and in two of the three working groups. One working group will be conducted in English only. If you would like to take your own interpreter for a different language into the room, please contact the conference secretariat at bolognaconference2010@oead.at.“ (Vienna BPF Handbook).

The „Stockholm agreement” will be used for the 2012 Bucharest Bologna Process Ministerial Conference, meaning English and the language of the host country (Romania), as well as the languages of the BFUG Chairs (Denmark and Azerbaijan), upon specific requests in this sense.

Taking into account the previous BPF, the proposed languages for the 3rd BPF will be English, French, German, Spanish and Russian plus the language of the host country (Romania) and the two languages of the BFUG Chairs (Danish and Azeri).

- The IO WG members are asked to:

- Endorse the revised timeline for the 3rd BPF preparations, while allowing for last minute adjustments at a later stage (Annex 2);

- Endorse the mechanism on finalising the list of invitees for the 3rd BPF;

- Endorse the language regime for the 3rd BPF;

- Discuss and endorse the sub-themes for the parallel sessions of the 3rd BPF according to the BFUG recommendations and the input received so far (Annex 4);

- Discuss the sources of possible background papers and keynote speakers for the 3rd BPF,

- Provide input for the main aims and structure of the 3rd BPF statement.