## IPN timeline
2010
July/August | Circulate draft work programme
September | Feedback / input from the WG
Send revised version of the work programme
Call for participation in subgroups
10 December | First meeting of "overview" experts subgroup to discuss and analyse the questionnaire
tbc | Collection of information on existing materials and activities
tbc | First meeting of website subgroup
December | Expert meeting on promotion of EHEA
2011
February | Network meeting
June | Activity report to WG on International Openness
September | Submission of WG report to BFUG
October / November | Round table on EHEA promotion
2012
April | Ministerial conference

## IPN work plan
Tasks (as defined by TOR) | Format | Chair | Members | Specific tasks | Timeline
Develop an overview of existing initiatives/activities by all members of the network in the field of promotion of national higher education systems & the EHEA (state of the art); | Subgroup | Germany (DAAD) |  | National level information and promotion materials (and how it is used) and activities (the National members defining what is for the information and what is promotion – ask them to do the differentiation) Promotion of the EHEA from the side of the National level What are the information gaps that they would like filled by EHEA sourced information? (some sort of needs analysis) | details to be agreed with Chair and subgroup
Support the Bologna Secretariat and the Working group "International Openness: European Higher Education in a Global Context" regarding the further development of specific information material (to be used e.g. at international fairs and visits) | tbc
Support the Bologna Secretariat and the Working group "International Openness: European Higher Education in a Global Context" regarding the further development of the EHEA Website for a global audience. | Subgroup |  |  | Aid in the build-up of the permanent EHEA website, especially the International Openess and Study in Europe sections
Identify EHEA characteristics fir for promotion and design measures to enhance the promotion of the EHEA and of national higher education systems as part of the EHEA. | Expert meeting | hosted by Austria | ACA, Chair of subgroup preparing overview (Germany), Barbara Weitgruber, chairs of the other groups (Mobility, Transparency, Recognition), EMA, Austrian representative (as host), IAU, Secretariat representative etc. (total: 10 people) |  | December 2010/ January 2011
Advise/support the Working Group "International Openness: European Higher Education in a Global Context" in convening a round table (with the participation of the European Commission and other main actors in higher education promotion in Europe) to devise a "road map" and to identify opportunities and actions for enhancing European-level promotion. | Subgroup with Chairs and members of IPN and WG Int. Openness |  |  |  | autumn 2011
Foster the exchange of good practice and know-how as well as peer learning in the field of national-level promotion of higher education in a European context. | via Network meetings; additional activities tbc